## Sheet1
Colour Legend
Black | Ready to start and scheduled in
Brown (Neutral) | Paid deposit but not scheduled in
Yellow | Work underway
Blue | Work finished and invoiced
All Blue | Invoice paid
Green | Job on hold or in future
Grey | Blinds
Hide | Hide line once warranty/maintenance document is sent
Job list
Client name | Phone number | Address | Site visit | Deposit payed | ordered | Pergola Type | Estimated start date | final payment | Job assigned to | completed | Lights | Blinds | Est. Days | size | Colour | Roofing | Ordered | number of sheets | Size | Frame colour | Comments
Kyle Bahn | 0210480984 | Workworth | B |  |  |  | 2021-10-18 | 2021-12-14 | B & D | [5 empty] | Plexi |  |  | 3 |  |  | Binds ordered 29/10/21
Naina | 0211089316 | 14 Eleanor Place | B | 2021-08-16 | Y |  | 2021-10-08 | 2021-10-20 | Dave | [5 empty] | Plexi |  |  | 6
Siyin Wang | 0226386356 | 18 Queen Mary Ave | B |  | y |  |  | 2021-11-15 | Dave | [5 empty] | Plexi |  |  | 5 |  |  | Blinds ordered
Francois | 02108295929 | 71 McLarin Glenbrook | B |  | y |  | 2021-10-27 | 2021-11-10 | Dave | [5 empty] | Colour Steel | [5 empty] | colour steel
Shiva Reddy | 02106855314 | 96 Seaview Glenfield | B |  | y |  | 2021-10-30 | 2021-11-04 | Dave | [5 empty] | Plexi |  |  | 2
Rudolf | 021560058 | Costa Viva | B |  | y |  | 2021-11-08 | 2021-11-12 | Dave | [5 empty] | Acrylic | [5 empty] | Supreme for the acrylic
Jeff | 021533398 | Hoskins | B |  | y |  | 2021-11-02 | 2021-11-22 | Dave | [5 empty] | Plexi |  |  | 2 |  |  | take down existing structure first
Rohil | 0211621626 | 22 Hava Place | B |  | y |  | 2021-11-10 | 2021-11-09 | Dave | [5 empty] | Plexi |  |  | 4 |  |  | Phoned and changed from satin to Matt Black 8/10/21
Chrissie | 021777343 | 3/63 Aldersgate Rd | B | 2021-10-01 | y |  | 2021-11-12 | 2021-11-18 | Dave | [5 empty] | Plexi |  |  | 5 |  |  | two covers Taitania
Lees & Andy | 021939098 | Halsey Drive | B |  | Y |  | 2021-11-17 | 2021-11-15 | Dave | [5 empty] | Plexi |  |  | 4 |  |  | waiting for the aluminium
Lisa Waihi | 0274545051 | 352D Woodlands Rd, Waihi | B |  | Y |  | Travel | 2021-12-23 | Bruce | [5 empty] | Corr |  |  |  |  | New Denim blue | When we can travel Bruce to do
Tania & Neal Jones | 02108310791 | 40 Myland Drive | B |  | Y |  | 2021-11-22 | 2021-12-01 | Dave | [5 empty] | Plexi |  |  | 1.5 |  | Matt black | extra joiner and use two sheet off cuts
Bob Plunket | 021730508 | 4 McLean St | B |  | Y |  | 2021-11-25 | 2021-12-09 | Dave | [5 empty] | Plexi |  |  | 4 |  | white/black | 1 pergola and a plexi roof added to an existing structure
Jolyon Harris | 0221260891 | 12 Opanuku Rd | B | 2021-10-19 | Y |  | 2021-12-02 | 2021-12-14 | Dave | [5 empty] | Acrylic |  |  |  |  | New Denim blue | Supreme for the acrylic 4m 13 sheets
Eric Heng | 02040320879 | 76a Empire Rd Epsom | B | 2021-10-26 | Y |  | 2021-12-08 | 2021-12-06 | Dave | [5 empty] | Plexi |  |  | 5 |  | Arctic white | 5 Z Brackets to raise roof 100mm above gutter 2 posts
Matthew Fell | 0274212747 | 18 Taumata Rd Sandringham | B | 2021-10-27 | Y |  | 2021-12-14 | 2021-12-29 | Dave | [5 empty] | Plexi |  |  | 3 |  | Appliance white | Blinds ordered copleted install invoice sent Paid | Bruce blinds
Matthew King | 0210634610 | 10 Godfrey Drive Orewa | J | 2021-10-28 | Y |  | 2021-12-20 | 2021-12-24 | Dave | [5 empty] | Plexi |  |  | 2 |  | Arctic white | delivered and installed and paid | Bruce Blinds
Andy Hepple | 021146495 | 25 Saltaire St Avondale | J | 2021-10-29 | Y |  | 2022-01-05 | 2022-01-20 | Dave | [5 empty] | Acrylic |  |  |  |  | Appliance white | 4m acrylic
Graham Gates | 021926223 | Paerata Rise Pukekohe | B | 2021-10-29 | Y |  | 2022-01-24 | 2022-01-27 | Dave | [5 empty] | Plexi |  |  | 3 |  | Flaxpod
Mark Garland | 0275555884 | 141 Victoria St, Onehunga | J | 2021-11-08 | Y |  | 2022-01-14 | 2022-01-17 | Dave | [5 empty] | Plexi |  |  | 1+ |  | light grey?
Gabrielle Caesar | 021574154 | 20 Claremont St, Grafton | J | 2021-11-09 | Y |  | 2022-01-18 | 2022-02-09 | Dave | [5 empty] | Plexi |  |  | 2.5 |  | Appliance white
David Percey | 0274774005 | 11A Grange Rd, Mt Eden | J | 2012-11-08 | N |  | 2022-01-21 | 2022-03-16 | Dave | [5 empty] | Plexi |  |  | 2+ |  | Arctic white | extra water proofing
Jarred Hemple | 02108583018 | 41 Vinistra Rd Kumeu | J | 2021-11-10 | Y |  | 2022-01-27 | 2022-02-09 | Dave | [5 empty] | Plexi |  |  | 3 |  | Matt black | Triangle fill in still to be done
Nesa Selvarajah | 021539010 | 27a Wilerton Ave | J | 2021-11-12 | Y |  | 2022-01-31 | 2021-12-31 | Dave | [5 empty] | Plexi |  |  |  |  | Karaka
Kylie Skinner | 0272965273 | 2 Maka Tce, Orewa | B | 2021-12-29 | Y |  | 2022-01-28 | 2022-03-01 | Dave | [5 empty] | Plexi |  |  | 2 |  | Flaxpod
Pratima Silva | 0212960982 | 11 Meadway | B | 2021-11-22 | Y |  | 2022-02-03 | 2022-02-08 | Dave | [5 empty] | Acrylic |  |  | 6 of 6m |  | Arctic white
Tania Beekmans | 0223400916 | 27 Hing St | B | 2021-11-29 | Y |  | 2021-02-04 | 2022-02-10 | Dave | [5 empty] | Plexi |  |  | 1+ |  | Matte Black
Ingrid McPhee | 02102233460 | 1 Ashley Ave, Long Bay | B | 2021-12-03 | Y |  | 2022-02-09 | 2022-02-17 | Dave | [5 empty] | Plexi |  |  | 1+ |  | Matte Sandstone grey
Angela Eng | 021425086 | 3a Siren | B | 2021-12-06 | Y |  | 2022-02-11 | 2022-02-15 | Dave | [5 empty] | Plexi |  |  | 2+ |  | Arctic white
Josh Farry | 0223134421 | 31 Ascension Cres | B | 2021-12-09 | Y |  | 2022-02-14 | 2022-03-01 | Dave | [5 empty] | Plexi |  |  | 3 |  | Matte Black
Marie Hansen | 0211467650 | 151 Annanandale Rd Kumeu | B | 2021-12-14 | Y |  | 2022-02-28 | 2022-03-09 | Dave |  |  | ..\Orders\9 02.xlsx |  |  | Plexi |  |  | 5+ |  | Appliance white
Kevin Hodges | 02108332407 | 8 Kate Sheperd Ave | B | 2021-12-14 | Y |  | 2022-01-10 | 2022-02-01 | Dave | [10 empty] | Gutter still to be fitted | Structure modified Plexi to be installed
Rebecca Sullivan | 0212398715 | 19a Castledine Cres | B | 2021-12-17 | Y |  | ? | 2022-03-25 | Dave |  |  | stock |  |  | Plexi |  |  | 2 |  | 4m gutter arctic white | Modify Structure add plexi
Alex | 0220376446 | 39 Tawariki | B | 2021-12-23 | Y |  | 2022-07-18 | 2022-09-01 | Dave |  |  | TBC |  |  | Acrylic |  |  |  |  | metro warm white PKS | 14 sheets 4m acrylic
Aster Magyawi | 0211821348 | 7/28 Taylor St BHB | J | 2021-12-24 | Y |  | 2022-02-21 | 2022-02-24 | Dave |  |  | ..\Orders\9 02.xlsx |  |  | Plexi |  |  | 3 |  |  | Gable 18m2
Tony and Jo Yu | 021992281 | 33 Wapiti Ave | B | 2022-01-12 | Y |  | 2022-02-04 | 2022-03-17 | Dave |  |  | https://netorgft8481712-my.sharepoint.com/personal/info_sanctuarypergolas_co_nz/Documents/Sanctuary%20Pergolas%20Bruce/Orders/Wapiti%20Ave.xlsx |  |  | Acrylic |  |  | 5x4m |  | Matt Appliance white | Light grey tint
Kylie Larsen | 021702487 | 89 Godfrey Drive, Millwater | B | 2022-01-13 | Y |  | 2022-03-14 | 2022-03-10 | Dave |  |  | ..\Orders\9 02.xlsx |  |  | Plexi |  |  | 3 |  |  | Pitched 6 x 3.1
Jenny Silby | 0211226826 | 7 Wendy Rd Waitakere Town | B | 2022-01-24 | Y |  | 2022-03-23 | 2022-03-31 | Dave |  |  | ..\Orders\11 02.xlsx |  |  | Plexi |  |  |  |  | Matte black | Pitched 6 x 3.1
Arul Veerasingama | 02102764623 | 9 Hughs way Flat bush | B | 2022-01-25 | Y |  | 2022-03-18 | 2022-03-28 | Dave |  |  | ..\Orders\11 02.xlsx |  |  | Acrylic 4m |  |  |  |  | Matte Black grey tint | 7m x 4m Blinds installed triangle to be installed | Bruce blinds
William Singleton | 02102949214 | 2-39A Konini Rd | J | 2022-01-27 | Y |  | 2022-03-25 | 2022-03-31 | Dave |  |  | https://netorgft8481712-my.sharepoint.com/personal/info_sanctuarypergolas_co_nz/Documents/01_Archive/03_Orders/220310.xlsx | [5 empty] | 2 |  | Mist green
K Huljich | 021846096 | 21 Sunderland Ave | J | 2022-02-04 | Y |  | 2022-03-30 | 2022-04-12 |  |  |  | https://netorgft8481712-my.sharepoint.com/personal/info_sanctuarypergolas_co_nz/Documents/01_Archive/03_Orders/220310.xlsx | [5 empty] | 5 |  | Flaxpod | Hip wraparound
Lynn Bonnington | 0272782061 | 145 Hanham Rd, Kumeu | J | 2022-02-08 | Y |  | 2022-04-04 | 2022-05-20 |  |  |  | https://netorgft8481712-my.sharepoint.com/personal/info_sanctuarypergolas_co_nz/Documents/01_Archive/03_Orders/hanham%20rd.xlsx | [5 empty] | 12x6m |  | acrylic Matte black | Gable 29m2
Harm | 0277744550 | 136 Voyager Drive | B | 2022-02-11 | Y |  | 2022-03-09 | Paid | Bruce |  |  | ..\Orders\11 02.xlsx |  |  | Nil |  |  | 0 |  | Matte silver pearl | Install pergola supplied by Auckland pergolas supply 2 beams
Ian Mundy | 0223647871 | 55 Jeroboam Loop, Kumeu | J | 2022-02-17 | Y |  | 2022-04-07 | 2022-05-02 | D | [5 empty] | Plexi |  |  | 4
Harrison | 0211489940 | 51 Couldrey | J | 2022-02-24 | Y |  |  | 2022-04-26 | [6 empty] | Plexi |  |  | 3
Greg Ross | 0272220221 | 56 Jack Patterson | J | 2022-02-24 | Y |  | done | 2022-05-02 | [6 empty] | Acrylic 4m |  |  | 19x4m |  |  | Blind ready to install Installed and Paid
Lisa giles | 021558794 | 23 Mita Rd, Silverdale | J | 2022-03-07 | Y |  | 2022-04-30 | 2022-05-06 | [6 empty] | N/A
M Rohr | 021416251 | 39 Surf Rd | J | 2022-03-11 | Y |  | 2022-05-04 | 2022-05-16 | [6 empty] | Plexi |  |  | 3 |  | mulford
Viky Haber | 0272940315 | 69 Botany Rd | B | 2022-03-23 | Y |  | before 1/5 | 2022-05-02 | [6 empty] | Plexi |  |  | 4 |  | 1 joiner dark colour M/B | Remove polycarb relpace with Plexi
Jon Jarvie | 0224145909 | 79 Schlaepfer Rd | B | 2022-03-23 | Y |  | 2022-05-11 | 2022-05-16 |  |  |  | *stock |  |  | Plexi |  |  | 2 |  | Mulford Arctic white | Add a 3m joiner from stock !!!!
Monique Brunel | 0212921681 | 17 Greenbank Dr | J | 2022-03-26 | Y |  | 2022-05-13 | 2022-06-03 | [6 empty] | Plexi |  |  | 5 |  | If we need supreme | try mulford first
Bronwyn Smith | 0212345321 | 49 Honey Rd, Waiuku | J | 2022-03-28 | Y |  | 2022-05-31 | 2022-06-21 | [6 empty] | Acrylic |  |  | 27x4m |  |  | Screens to be installed Blind ordered
Troy Evans | 0212238525 | 3 Phelps Place | J | 2022-04-06 | Y |  | 2022-06-13 | 2022-07-05 | [6 empty] | Plexi |  |  | 2 |  | Brian
A Mellick | 0211677123 | 9 Stallard | B | 2022-04-08 | Y |  | 2022-06-13 | 2022-06-15 | [6 empty] | Plexi |  |  | 3 |  | Ironsand | Soffit brackets and upgrade gutter
Rebacca Stanley | 0223439546 | 4/5 Charmaine Cr Hamilton | J | 2022-04-13 | Y |  | 2022-07-18 | 2022-07-25 | [6 empty] | Plexi |  |  | 3 |  | Appliance white
Diane Jackson | 021315339 | 16 Arapuni Ave Onehunga | J | 2022-04-13 | Y |  | 2022-06-16 | 2022-06-21 | [6 empty] | Plexi |  |  | 1 |  | Arctic white
Michelle | 021646090 | 27A Southern Cross Rd, Kohimarama | J | 2022-04-15 | Y |  | 2022-06-20 | 2022-07-05 | [11 empty] | Matt Black
Greg Tunnell | 0211076051 | 5 Paewai Rd, Glen Eden | J | 2022-04-19 | Y |  | 2022-06-27 | 2022-06-29 | [11 empty] | Appliance White | Soffit Brackets and 100 x 100 posts & front beam
Anna Lim | 0212779995 | 18 Westmere Park Ave | J | 2022-04-20 | Y |  | 2022-06-30 | 2022-07-11 | [6 empty] | Acrylic (Clear) 4m |  |  |  |  | Metropolis electric cow
van den Hoofdakker | 021810771 | 1/110A Gowing Dr, Meadowbank | J | 2022-04-28 | Y |  | 2022-07-05 | 2022-07-11 | [11 empty] | Appliance white
Mel Tong | 0211505712 | 11 Arapuni Ave, Onehunga | J | 2022-05-04 | Y |  | 2022-07-11 | 2022-08-17 | [11 empty] | Matt Black | Lights to be installed
David Perkins | 0274583833 | 2 Ngapawa St, Sandringham | J | 2022-05-05 | Y |  | 2022-07-07 | 2022-08-16 | [11 empty] | Arctic White | Lights to be installed
L T Bates | 02102440814 | 18 Wairoa Rd, Narrow Neck | J | 2022-05-19 | Y |  | 2022-07-12 | 2022-08-05 | [11 empty] | Gravel Matt | Soffit brackets, 8 lights to be installed
Megan Potter | 0273704329 | 3 Huia Street, Tahuna | J | 2022-05-20 | Y |  | 2022-07-12 | 2022-07-25 | [6 empty] | Coloursteel |  |  |  |  | Grey Friars | Gable With truss
Pablo Dunovits | 021754268 | 14 Derwent Cres, Titirangi | J | 2022-05-22 | Y |  | 2022-07-14 | 2022-09-05 | D | [11 empty] | blind to be installed
H Macmillan | 0278142139 | 3002B SH16 | J | 2022-05-26 | Y |  | 2022-07-02 | 2022-09-27 | D
Tanya Tudman | 021318438 | 170 Ninth view Ave | B | 2022-05-26 | Y |  | 2022-07-26 | 2022-08-08 | D | [5 empty] | Acrylic |  |  | 10x4m, 7x3m |  | Matt black | Hip with overhang
Diego Barrese | 021798717 | 25 Longburn | B | 2022-05-28 | Y |  | 2022-07-29 | 2022-09-05 | D | [5 empty] | Plexi |  |  | 2 |  | Appliance white | inverted gable
C Hanley | 0276221626 | 16 Chadwell St | J | 2022-06-01 | Y |  | 2022-07-19 | 2022-07-19 | [6 empty] | Acrylic
J Donnan | 0277284235 | 92a Nile Rd | R | 2022-06-08 | Y |  | 2022-08-01 | 2022-08-08 | J | [5 empty] | Plexi |  |  |  |  | Matt Black | pitched with gutter and 4 soffit brackets
A Sutton | 0212796804 | 60 Fairmount Rd | R | 2022-06-13 | Y |  | 2022-08-04 | 2022-09-06 | J | [5 empty] | Plexi |  |  | 3 |  | Silver pearl | Pitched with suffit brackets
Agnes Maat | 0221013342 | 107 Domain Rd | B | 2022-06-13 | Y |  | 2022-08-22 | 2022-08-29 | D | [5 empty] | Plexi |  |  | 3 |  | Matt off white
Genna Peka | 0211506873 | 1 Elliot St Waihi | B | 2022-06-23 | Y |  | 2022-08-31 | 2022-09-21 | D | [10 empty] | Greyfriers | One pergolas and a carport 6x3
Andrew Benton |  | 47 Esplanade | J | 2022-06-23 | Y |  | 2022-08-25 | 2022-10-20 | J
Mike Tappin | 021786335 | 11 Nobilo Kumeu | B | 2022-06-27 | Y |  | 2022-09-07 | 2022-09-27 | D | [10 empty] | Blinds?
Ken G Parry | 0274973823 | 516B New North Rd | R | 2022-07-05 | Y |  | 2022-09-13 | 2022-09-16 | J |  | x | B |  |  | Plexi |  |  |  | deposit for blinds paid | Binds to be installed
Paresh Patel | 0211034464 | 143A Taylor St | B | 2022-07-13 | Y |  | 2022-09-12 | 2022-09-15 | D | [5 empty] | Plexi |  |  | 1.5 |  | Matt New Denim blue
Maryfrances Wells | 0210494641 | 10A Campbell Place | B | 2022-07-18 | Y |  | 2022-09-14 | 2022-09-22 | D | [5 empty] | Plexi |  |  |  |  | 9x3.1
Carrie Bonner | 0225986081 | 19 Warrington Rd Remuera | R | 2022-07-20 | Y |  | 2022-09-16 | 2022-09-27 | J | [5 empty] | Acrylic |  |  |  |  | 3.5x3.7 From stock!
J M Cassin | 021892910 | 120 waiheke Rd, Onetangi | R | 2022-08-01 | Y |  | 2022-10-03 | 2022-11-14 | D | Y | x | x | [5 empty] | Gable fill-in and blinds
K C Watson | 0275129081 | 51 Te Paea Ave, Paerata | R | 2022-08-04 | Y |  | 2022-09-22 | 2022-10-07 | D
Chris Bullen | 0274692496 | 87 Valley Rd, Mt Eden | B | 2022-08-12 | Y |  | 2022-09-22 | 2022-10-04 | J | [5 empty] | Light grey plexi
Bronwyn Smith | 0212345321 | 49 Honey Rd, Waiuku | J | 2022-08-26 | N |  | 2023-01-10 |  | D | Y | 12 | x
Babara Stevens | 021669533 | 49 Tawhiri Rd, One Tree Hill | J | 2022-08-16 | Y |  | 2022-10-06 | 2022-11-08 | J | Y | x | x |  |  | Acrylic |  |  | 14x6m | 9m x 4.8m | TBC
Louise Atkins | 02102523056 | 37C Onewa Rd | J | 2022-08-19 | Y |  | 2022-10-12 | 2022-10-26 | J | Y | L | X | [6 empty] | 4.8m x 3m | Matt Black | 6 Downlights
Terrance Christy | 021744182 | 10 Notre Dame Way, Albany | R | 2022-08-19 | Y |  | 2022-10-14 | 2022-11-01 | D | Y | X | X | [5 empty] | problems with water overshooting the gutter
Anna Cunningham | 0212376292 | 91 First View Ave, Beachlands | J | 2022-08-22 | Y |  | 2022-10-24 | 2022-12-24 | J |  | x | x |  |  | try start before 7/10 |  |  | waiting for sheets seven 4m | 4.5m x 4m | Appliance White | 100x100 Posts
Jmak Investments | 0274046156 | 8 Brown St, Little Manly | R | 2022-08-22 | Y |  | 2022-10-19 | 2022-11-10 | D | Y | x | x |  |  | Mark Elliott |  |  | power by pool pump | 2.4m x 9.4m | Silver Pearl
Laura Stephens | 0277755061 | 41 Covil Ave, Te Atatu South | J | 2022-08-22 | Y |  | 2022-10-25 | 2022-11-07 | D | Y | [8 empty] | 6.5m x 2.9m | Ironsand
Scott Power | 021739166 | 103 McKellar Pl, Whangamata | J | 2022-08-25 | Y |  | 2022-10-18 | 2022-11-03 | J | Y | [8 empty] | 6m x 4m | Silver Star - Double Check
Sandra Dodson |  |  | B | 2022-08-29 | Y |  | 2022-10-24 | 2022-12-19 | J |  | L | x |  |  | lights - holes and wire only
Neubert Gunth | 021557758 | 71a Selwyn Ave, Mission bay | R | 2022-08-30 | Y |  | 2022-10-08 | 2022-11-17 | J | Y | x | x |  |  | 100x100 Gutter against house with internal spacers |  |  |  | 2m x 5/6m | Flax Pod
Brett Haeger | 021884903 | 1 Lennon Access Rd, Stillwater | J | 2022-08-31 | Y |  | 2022-10-28 | 2022-12-28 | B |  | x | B |  |  | posts to go on the outside of front beam so gutter cut out of off cut |  |  |  | 3.1m x 5m fall | Ironsand
Camila Pardal | 027 789 0012 | 3 Maclachlan Way Pokeno | J | 2022-09-02 | Y |  | 2022-11-02 | 2022-11-21 | D | Y | 8 | x |  |  | Cut gutter out of front beam off cut
R Hoskins | 021658019 | 9 Chapman Rd, Te Atatu Peninsula | J | 2022-09-05 | Y |  | 2022-11-10 | 2022-11-30 | J | Y | x | x |  |  | Ironsands |  |  | Start no later than the 7/11/22
Miho Watanabe | 021315806 | 1 Tesla Place, Totaravale | R | 2022-09-07 | Y |  | 2022-11-10 | 2022-11-17 | D | Y | x | x |  |  | NDB |  |  |  | 3.5m x 1.3m | New Denim Blue
M Schlitter | 0224082618 | 10 Secoia Cr, Mangere | J | 2022-09-07 | Y |  | 2022-11-17 | 2022-11-30 | D |  | x | x |  |  | Matt Black
R A Tablizo | 0211363024 | 4B Thomas Rielly Ave, Hobsonville | R | 2022-09-07 | Y |  | 2022-11-10 | 2022-11-18 | N | Y | x | x |  |  | Matt Black |  |  |  | 5.0m x 2.9m
Alex Moffatt | 021443070 | 21 Verona Avenue, Mount Albert | J | 2022-09-07 | Y |  | 2022-11-11 | 2022-12-09 | J |  | 10 | x |  |  | Appliance white |  |  | some materials from stock
Anna Smith | 0273021383 | 14Q Cradock St, Avondale | R | 2022-09-09 | Y |  | 2022-12-09 | 2022-12-19 | J |  | x | x |  | 4x4 | Flaxpod |  |  |  | 4.1m x 3.9m | Flax Pod
Graham Gates | 021926223 | 53 TePaea Ave | J | 2022-09-12 | Y |  | 2022-11-22 | 2022-12-13 | D |  | x | x |  |  | Flaxpod
Frances VanDammen | 021506483 | 202 Oraha Rd, Kumeu | R | 2022-09-12 | Y |  | 2022-11-28 | 2022-12-20 | D |  | x | x |  | 3x4x2 | Clear Matt Black |  |  | Gable acrylic
Vicki Bishop | 0210547125 | 224 Birdwood Rd, Massey | J | 2022-09-19 | Y |  | 2022-11-23 | 2022-11-30 | J |  | x | x |  | 6x3 |  |  |  |  | 6x3
Dannyn Leong | 0278949431 | 42 Landing Rd | R | 2022-09-21 | Y |  | 2022-11-28 | 2022-12-22 | J |  | x | x |  | 5x4 | Appliance white |  |  |  |  | Appliance white | 8 lights
Stephen Usmar | 0274826889 | 25 King Richard Place, Browns bay | J | 2022-09-22 | Y |  | 2022-12-06 | 2023-02-15 | J |  | 12 | x |  |  | Before Christmas |  |  |  | 56m2
Alison Sutton | 0212796804 | 60 Fairmont Rd Titirangi | B | 2022-09-26 | Y |  | 2023-01-20 | 2023-02-09 | J |  | x | B |  |  | Blinds |  |  | horizontal blinds ready | Blinds
R & A Murphy | 0288510251343 Aberdeen Cres, Wattle Downs |  | R | 2022-10-03 | Y |  | 2023-01-30 | 2023-02-09 | D |  |  |  |  | 4.1x3 | greyfriers |  |  | Still to do a Square above the entrance
Kelly Floyd | 027 2800715 | 133 Stanmore Bay Rd, Whangaparoa | J | 2022-10-04 | Y |  | 2022-12-09 | 2022-12-28 | D | [8 empty] | gutter from stock | 3m x 3m | Appliance White | 1.5 6m j
Jo Chan | 0211302339 | 43 Scarborough Tce, Parnell | J | 2022-10-07 | Y |  | 2022-12-15 | 2023-02-01 | D | [8 empty] | Gutter from stock | 3.2m x 1.5m | Matt Black | 1.5 6m j
BTS Construction | 021 609 586 | 1137A Whangaparoa Rd | J | 2022-10-10 | Y |  | 2022-12-14 | 2023-02-24 | D | Y | [8 empty] | 8.8x3 |  | 3 6m j
Frank Clarke | 021814814 | 316 Hill Rd, The Gardens | B | 2022-10-10 | Y |  | 2022-12-16 | 2023-01-30 | J | Y |  |  |  |  | Try before the 10/12/22 |  |  | plexi | 2.3x1.4 and 4.2x3.1 | Ghost grey | 1 6m j
Simon Akiko | 021 680 688 | 14 Mellefont Close, East Tamaki | J | 2022-10-30 | Y |  |  |  | J | Y | 21 |  |  |  | Charcoal Matt |  |  | 22/02/23 $15100 pd - $1400 outstanding? | 8.8x5 | 15 of 6m joiners | 15 6m j
Blair Cressy | 021918576 | 235 Glenfield Rd, Hillcrest | J | 2022-10-31 | Y |  | 2023-01-20 | 2023-02-27 |  | Y |  |  |  |  | Appliance White |  |  |  | 6x3 |  | 2 6m j
Nick Donnan | 0277284235 | 92a Nile Rd | B | 2022-11-01 | Y |  | 2022-12-20 | 2023-04-11 | S | Y |  |  |  | 3m | matt Black |  |  | Fill ins
Richard Unsworth | 0276600606 | 1/136 Taylors Rd, Mt Albert | J | 2022-11-03 | Y |  | 2023-01-25 | 2023-04-19 | J | Y | x |  |  | 7.3x3.4 | Grey Friars |  |  | Acrylic
Deb Hay | 0212525742 | 8 Wilk Lane, Browns Bay - Unit 15 | J | 2022-11-08 | Y |  |  | 2023-01-31 |  | Y | x |  |  | 4x3 | Grey Friars |  |  | Plexi Clear |  | Grey Friars
Debbie McKenzie | 0274261562 | 34 Max Short Dr, Pukekohe | J | 2022-11-10 | Y |  |  | 2023-03-23 | D | Y | x | Y |  | 4.5x4 | Ironsands Matt |  |  | Plexi
William Cairns | 021521521 | 161 The Drive Christie Ho | B | 2022-11-11 | Y |  |  | 2023-02-08 | D | Y
Ron Gribble |  |  | B | 2022-11-23 | Y |  |  | 2022-11-23 | D | Y | X | X |  | 5x2
Bronwyn Smith | 0212345321 | 49 Honey Rd, Waiuku | J | 2022-11-25 | Y | Invert Pitched |  |  | J | Y | Yes | 2 |  |  | Matt Black |  |  | Infills and louvers
Glynis Ryder | 0272922405 | 101 Kennedy Rd, Dairy Flat | J | 2022-11-30 | Y |  |  | 2023-03-23 | D | Y |  |  |  | 8.5x3.3 | Matt Black |  |  | Large Gable, 150x50 rafters, 200x50 beams clear end panels
Robert, Linda Gagnon | 021611772 | 6 Porokaiwhiri Ave, Helensville | J | 2022-12-09 | Y |  |  | 2023-02-24 | J | y |  |  |  |  | Matt Black |  |  | Plexi, Brackets, Blinds 2.7m | 4.9m x 2m, 8m x 2m
J&S Cousins | 0274880081 | 204 Carrington Rd, Mt Albert | J | 2022-12-13 | Y |  |  | 2023-03-21 | J | Y |  |  |  |  | Appliance White |  |  | Plexi, Brackets | 7m x 2m, 7m x 3m
Stephen Usmar | 0274826889 | 25 King Richard Place, Browns bay | J | 2022-12-14 | Y |  |  | 2023-02-15 | J | Y | [7 empty] | Fix leaks
Karl Symons | 0272228576 | 11 Whites Way, Ellerslie | J | 2022-12-15 | Y |  |  | 2023-03-28 | D | Y | [8 empty] | 6.9m x 2m
Jason Bruce | 027 495 5002 | 49 Wellesley Rd, Mangere Bridge | J | 2022-12-16 | Y |  |  | 2023-03-15 | J | Y
Susan Blacklaws | 0278700037 | 8 Delphi Grove, Tuakau |  | 2022-12-20 | Y |  |  | 2023-02-28 | J | y | [7 empty] | s.blacklaws@outlook.com | 4m x 3m
Louise Teoh | 0274075934 | 18 Alton Ave, Hillcrest | J | 2022-12-28 | Y |  |  | 2023-02-28 | D | y | x | x |  | 5x3 | Matt Black |  |  | lteoh@xtra.co.nz
Tony and Jo Yu |  |  | B |  |  |  | March |  | B | Y | [7 empty] | Fix Leaks
Frank Clarke | 021814814 | 316 Hill Rd, The Gardens | B | 2023-01-09 | Y |  |  |  | D | Y | No | No |  |  | Ghost Grey
J G Donkin | 021617141 | 48 Greenhithe Rd, Greenhithe | J | 2023-01-17 | Y |  | 2023-04-03 | 2023-04-11 | J | Y | 8 | [6 empty] | Lights | 3m x 3m, 4.5m x 3m
Ben Vosloo | 0277001703 | 25 Ranchod Terrace, Pukekohe | J | 2023-01-27 | Y |  |  | 2023-03-31 | J | Y | X | X |  |  | Matt Olive |  |  | benthevetsa@gmail.com
Karen Raynes | 0272243073 | 269 Karioitahi Rd, Waiuku | J | 31/02/23 | y |  | 2023-04-04 |  | D | Y | 12 | Y |  |  | New Denim Blue |  |  | karen.raynes@icloud.com | Gable, additional gable infill, blind, lights
Maya | 0211385796 | 24 Kirby St, Glendene | S | 2023-02-23 | y |  |  | 2023-03-20 | S | Y | [7 empty] | Replace polycarb
Angela Eng | 0226321585 | 3a Siren St, Milldale (Silverdale) | B | 2023-02-22 | y |  |  | 2023-04-04 | J | Y |  |  |  |  | Arctic White
Pantika Banerjee | 0212921886 | 14 Manhattan Rise, Orewa | R | 2023-02-28 | y |  | 2023-04-12 | 2023-04-24 | D | y |  |  |  |  | Flaxpod |  |  | Install before 15th April if possible
Debbie McKenzie | 0274261562 | 34 Max Short Dr, Pukekohe | S |  | y |  |  | 2023-03-23 | S | Y |  |  |  |  | Ironsands Matt |  |  | Blind and infills with 50x50 framing
Le Chu | 021 923 211 | 18 Bob Charles Dr, Golflands | S | 2023-03-02 | y |  | 2023-04-11 | 2023-04-21 | J | Y |  |  |  |  | Ironsands Matt |  |  | One post, fall back into to house 3.9m wide x 3m sloping
Becroft Builders | 021 860 222 | 383 Pt Chevalier Rd, Pt Chev. | J | 2023-03-02 | y |  | 2023-04-20 | 2023-05-01 | D | Y |  |  |  |  | Matt Black |  |  | Isaac
Carl Mills | 0276732275 | 9 Otau Mountain Rd, Clevedon | R | 2023-03-07 | y | Invert Pitched | 2023-06-19 | 2023-08-24 | D | Y | No | No |  |  | Appliance White
Jane Hoogerbrug | 0272756996 | 39 Rothesay Bay Rd, Rothesay Bay | R | 2023-03-10 | y |  | 2023-04-17 | 2023-06-05 | J | Y | No | No |  |  | Matt Titania
Puneet Datta | 021711150 | 16 Tidal View Rd, Karaka | S | 2023-03-14 | y |  | 2023-04-01 | 2023-05-04 | D | Y | No | No |  |  | Matt Black |  |  | Record of Work LBP David Hartmann
Donna Handley | 027 521 2298 | 5 Tolben Pl, Golflands | J | 2023-03-20 | y |  | 2023-05-05 | 2023-05-09 | D | Y |  |  |  | 5x3m | Appliance White |  |  | Plexi. Brackets
Catherine Eastwood | 0211560602 | 10 Linwood Ave, Mt Albert | J | 2023-03-27 | y |  | 2023-05-09 | 2023-05-15 | J | Y |  |  |  | 6x2m | Appliance White |  |  | Plexi. Brackets
Mamakan Laureijs | 027 2209107 | 627 Huia Rd, Parau | S | 2023-03-27 | y |  | 2023-05-10 | 2023-06-01 | D | Y | No | No |  |  | Matt Ragoon Green |  |  | Twisted pitch freestanding
Andres Alcoba | 021404831 | 37 Athlone Rd, Glendowie | J | 2023-04-04 | y |  | 2023-05-18 | 2023-05-25 | D | Y | No | No |  | 8x3m | Grey Friars |  |  | Plexi
Leanne Freeman | 027 276 7061 | 11 Sadgrove Trc, Mt Albert | S | 2023-04-04 | y |  | 2023-04-28 | 2023-05-14 | J | Y | No | No |  |  | Black and Appliance White
Steven Chen | 0211793738 | 8a Merivale Ave, Epsom | J | 2023-04-11 | y |  | 2023-05-15 |  | J | Y | No | Yes |  |  | Ironsands |  |  | Plexi | 7.2mx2.2m + 4mx1.4m
Sunnie Ko | 02102785206 | 59 Waituarua Dr, Takanini | J | 2023-04-11 | y |  | 2023-05-24 | 2023-05-31 | D | Y | No | No |  |  | Grey Friars |  |  | Acrylic Strips | 3.7x4.1m
Greg Dean | 027 2468 009 | 37 Ocean Rd, Waikeke | B | 2023-04-20 | Y | Hip | 2023-06-12 | 2023-08-05 | J | Y | No | No |  |  | Matt Appliance white
Dina Heylen | 021 770988 | 30B The Parade, St Heliers | J | 2023-04-21 | y |  | 2023-06-09 | 2023-04-21 | D | Y | No | No |  |  | Appliance White |  |  | Opal Plexi
Redsons Ltd | 021 760 760 | 23 Glenview Rd, Glen Eden | S | 2023-04-26 | y |  | 2023-05-23 | 2023-07-17 | J |  | No | Yes |  |  | Black |  |  | Side wall infills above handrail and Ziptrak
Woody Au | 0212363717 | 16 Papaview Rd, Papakura | S | 2023-04-26 | y | Gable | 2023-05-31 | 2023-06-13 | D | Y | No | No |  |  | Flaxpod |  |  | Light Grey Plexi Gable with infills on both gable ends
Sue Bielby | 0274877680 | 41 Wairiki Rd, Mt Eden | S | 2023-04-27 | y |  | 2023-05-31 | 2023-06-13 | J |  | No | No |  |  | Appliance White |  |  | Crystalite - remove old pergola
Renovation Builders | 021 114 9943 | 73 Roberts Rd, Bayswater | S | 2023-05-01 | Y | Invert Pitched | 2023-06-26 | 2023-08-01 | J |  | 12 | No |  |  | Flaxpod |  |  | Plexi Inverted pergola. LBP required. Louver slat panels | 8m x 3m
Nick McCorkindale | 0274404230 | 5 Keshvara Rd, Beachlands | J | 2023-05-08 | y |  | 2023-06-13 | 2023-07-04 | J |  | 12 | No |  | 6x3m | Matt Black
Steve Callander | 0273522812 | 2/36 Penney Ave, Mt Roskill | S | N/A | Y | Pitched | 2023-08-12 | N/A | S&J |  | Yes | No |  | 4x3m | Matt Sandstone Grey |  |  | 4m x 3m with plexi
Carla Dukeson | 0212243933 | 2 McKenzie Ave, Arkles Bay | B | 2023-05-09 | Y | Gable | 2023-06-14 | 2023-08-02 | D |  | 12 | Yes |  | 8x2.5m | Mat Black |  |  | 8m x 2.5m Gable with 5 brackets made on site with packers
Karen Raynes | 0272243073 | 269 Karioitahi Rd, Waiuku | S | 2023-05-15 | Y | Blinds | 2023-06-08 | 2023-06-12 | S | Y | No | Yes |  | Blinds | Matt Black |  |  | 2x Omni Urban Mesh Galaxy
Peter Colenbrander | 021 337 739 | 419 Riddell Rd, Glendowie | S | 2023-05-12 | Y |  | 2023-07-03 | 2023-07-07 | J&J |  | No | No |  | 3.3x1.6 | Flaxpod |  |  | Plexi pergola over entry and fence frame with SS wire
Mel Firmin | 021637496 | 43 Arthur St, Freemans Bay | J | 2023-05-16 | Y |  | After July 8th |  |  |  | No | No |  | 3.1x7m | Appliance White |  |  | 8mm sheets @ 900mm centres (CLEAR) Refund of deposit 10/07/23
Frank Clarke | 021 814 814 | 316 Hill Rd, The Gardens | B | N/A |  | Pitched | 2023-08-01 | 2023-08-10 | D |  | No | No |  |  | Ghost Grey |  |  | Extend existing lower pergola as discussed
Jane Hoogerbrug | 0272756996 | 39 Rothesay Bay Rd, Rothesay Bay | S | 2023-06-05 | Y |  | 2023-07-06 | 2023-07-14 | J |  | No | No |  |  | Titania |  |  | Extend Entry pergola by 2 bays along side path
Garry Ivill | 021494949 | 17 Kesteven Ave, Glendowie | J | 2023-05-22 | Y | Gable | 2023-07-18 | 2023-08-27 | D | Y | 16 | No |  | 5x4.6m | Matt Black |  |  | Gable
Kirsten Tane | 0226434654 | 17 Arlose Place, Westgate | J | 2023-05-23 | Y | Pitched | 2023-08-02 | 2023-08-02 | D |  | No | No |  | 5x1.5m | Matt Black |  |  | Vertical panel 1.5x2.2m
Kumar Aravinda | 021594497 | 10/42 Codrington Crs, Mission Bay | S | 2023-06-01 | Y | 3x Pitched | 2023-07-10 | 2023-09-20 | J&J | Y | 22 | Yes |  |  | Ironsands |  |  | 3x Pitched Pergolas, 7x Ziptraks, 3x Omni Blinds
Puneet Datta | 021711150 | 16 Tidal View Rd, Karaka | S | 2023-06-06 | Y | Blinds/Infill | 2023-07-13 | 2023-10-12 | S | Y | No | Yes |  |  | Matt Black |  |  | 4x Blinds (Urban Mesh) and gable infill
Weymouth Primary | 092695088 | 23 Evans Rd, Weymouth | S | 2023-05-22 | Y | Pitched and deck | 2023-07-04 | 2023-07-17 | D |  | No | No |  | 6x1.35 | Matt Appliance White |  |  | Pitched Pergola and deck
Nick France | 0272018869 | 40b Tauoma Crs, Stonefields | S | 2023-05-31 | Y | Canceled |  |  | Jesse |  | No | Yes |  |  | Matt Appliance White |  |  | Pitched Pergola 5m x 2.9m sloping. Ziptrak and infill
Sunnie Ko | 02102785206 | 59 Waituarua Dr, Takanini | S | 2023-05-31 | Y | Pitched | 2023-06-23 | 2023-07-07 | S | Y | No | Yes |  |  | Matt Black |  |  | Ziptrak blind Urban mesh
Blair Giles | 021544480 | 69 Malvern Rd, Mt Albert | J | 2023-06-01 | Y | Pitched | 2023-07-24 | 2023-08-02 | J | Y | No | No |  | 3x2 | Appliance White |  |  | Plexi light grey
Bryce Mills | 0211163500 | 25a Cormack St, Mt Roskill | S | 2023-06-01 | Y | Blinds only | 2023-07-10 | 2023-07-11 | S | Y | No | Yes |  |  | PVC with black frame
Steve Hooper | 0274532577 | 66 Duke St, Mt Roskill | S | 2023-06-01 | Y | 2x Pitched | 2023-08-01 | 2023-08-12 | D | Y | No | No |  | 3.4x2.2 | Arctic White |  |  | 2 Pergolas - Back deck and side entry
Luke Barnes, Rohanna | 021621520 | 40 Mulgan St, New Windsor | S | 2023-06-01 | y | Invert Pitched | 2023-08-02 | 2023-08-24 | J | Y | 12 | No |  | 11x3 | Matt Appliance White Duratec |  |  | Inverted pergola- owner to arrange gutter bracket
Resolution Builders | 02102905828 | 629 Manukau Rd, One Tree Hill | S | 2023-06-06 | y | Pitched | 2023-08-07 | 2023-08-10 | D | Y | No | No |  | 3.1x3.1 | Silver Pearl |  |  | Pitched pergola attached to new weatherboards
Jerald Guillermo | 0211425843 | 7 Cooladawson Drive, Flatbush | J | 2023-06-06 | y | Pitched | 2023-08-14 | 2023-08-18 | J&A | Y | 8 | No |  | 5x4m | Matt Black
Fiona Willis | 0212150067 | 9A Summit Dr, Mt Albert | J | 2023-06-07 | y | Pitched/Gable | 2023-08-21 | 2023-09-14 | D | Y | No | No |  |  | Matt Appliance White |  |  | Two pergolas - see models
Vivienne Bullock | 0220880739 | 56 Parau St, Three Kings | S | 2023-06-08 |  |  | 2023-07-05 |  |  |  | No | No |  | 4.2x1.9 | Matt Appliance White |  |  | Plexi and joiners only
Clegg Builders-Tosh | 021962041 | 3b Seaview Trc, Mt Albert | S | 2023-06-14 | y | Pitched | 2023-08-18 | 2023-08-29 | J&A | Y | No | No |  | 2.7x1m | Ironsands |  |  | Entry canopy - Plexi
Alex Fitzgerald | 0212253702 | 8 Wakelin Rd, Beachlands | S | 2023-06-16 | y | Pitched | 2023-09-05 | 2023-09-16 | Al | Y | 8 | no |  | 5x4m | Matt Black |  |  | Pitched pergola over ground floor deck with 8 lights
Dione Hankins | 0211143322 | 380 Ponga Rd, Papakura | S | 2023-06-21 | y | Level frame only | 2023-09-05 |  | B&S | Y | No | No |  | 4.8x3.3 | Matt Black |  |  | Level Frame only- 200x50 Boundary with 150x50 rafters
Maneesh Deva | 0212254279 | 1 Ingram Rd, Remuera | S | 2023-06-21 | y | Twin Gables | 2023-08-22 | 2023-10-30 | J&A | Y | Yes | No |  | 5.5x5.3 | Matt Black |  |  | Double gable with hips and side slats (Electrical to be confirmed)
Elizabeth Ogden | 0212226786 | 19 Ladies Mile, Manly | S | 2023-06-21 | y | Pitched | 2023-09-07 |  | D |  | No | No |  | 7x4 | Appliance white |  |  | Pitched
Murray Rowe | 0274969694 | 5 Ngatoto Rd, Tinopai | J | 2023-06-28 | Y | Gable | 2023-11-28 | 2023-12-14 | J | Y | 16 | No |  | 8.9x5m | Matt Sandstone Grey |  |  | Gable - oversized gutter
Deb Hay | 0212525742 | 8 Wilk Lane, Browns Bay - Unit 15 | S | 2023-07-06 | y | Pitched extension | 2023-09-21 | 2023-09-27 | D | Y | No | No |  | 3x3.1 | Grey Friars |  |  | Extend existing lower pitched pergola to edge of deck
Paula Gardner | 0212535907 | 2/23 Rawhiti Rd, Manly | S | 2023-07-09 | y | Insulated | 2023-09-19 | 2023-09-22 | D | Y | No | No |  |  | Matt Titania |  |  | Thermal panels over existing conservatory and twinwall over carport
Jaimee Orellana | 02040992393 | 11D Welby Pl, Mangere | J | 2023-07-11 | y | Pitched | 2023-10-16 | 2023-10-19 | Al | Y | No | No |  | 4x3m | Matt Black |  |  | Remove existing structure but reuse 100x100mm posts
Hone Tobin | 0211012161 | 35 Lowtherhurst Rd, Massey | J | 2023-07-13 | y | 2x Pitched | 2023-10-02 | 2023-11-01 | D | Y | 16 | No |  | Two of | Desert Sand |  |  | 10.6x6m and 5.2x2.6m Pitched
Mamakan Laureijs | 0272209107 | 627 Huia Rd, Parau | J | 2023-07-18 | y | Side panels | 2023-08-10 | 2024-04-03 | D | Y | No | 3 |  |  | Matt Rangoon Green |  |  | Side panels and 3x blinds- $5000 payment 3/01/24
John Givan | 0210381846 | 198 Sinclair Rd, Ararimu | B,S | 2023-07-18 | y | Insulated/Arcylic | 2023-10-14 | 2023-10-13 | Al | Y | 6 | No |  | 8x4.8 | Matt Titania |  |  | Pitched Pergola Inslated panels and acrylic. Lights. Using existing timber posts and front beam
Phillip Muir | 021625798 | 32 Old Coach Way, Ramarama | S | 2023-07-18 | y | Pitched pergola | 2023-10-29 | 2023-10-03 | Al | Y | No | No |  | 3x2 | Matt Black |  |  | Pitched pergola over ground floor entry
Loren Swanson | 0212170415 | 22 Portsea Pl, Birkenhead | S | 2023-07-18 | y | Pitched pergola | 2023-10-03 | 2023-10-11 | D | Y | No | No |  | 7.9x2.4 | Matt Black |  |  | Pitched pergola over first storey deck
Robert, Linda Gagnon | 021611772 | 6 Porokaiwhiri Ave, Helensville | S | 2023-07-20 | Y | Ziptrak Blind | 2023-08-10 | 2023-08-12 | S | Y | No | Yes |  |  | Matt Black |  |  | Ziptrak Blind with small infill
Sam Yeo | 021985125 | 2 Halcombe Pl, Green Bay | J | 2023-07-25 | Y | Pitched | 2023-10-18 | 2023-10-26 | D | Y | No | No |  | 6x3m | Appliance white |  |  | Downpipe through deck and connect with house downpipe
Amanda - Goodhome | 027 777 0698 | 260 Great South Road, Takanini | J | 2023-07-20 | Y | Big Gable | 2024-01-29 | 2024-04-03 | D | Y | No | No |  |  | Matt Appliance White |  |  | Gable with decrative front end
Jo Kelly-Tucker | 0275437041 | 5a Peet Ave, Royal Oak | S | 2023-07-28 | Y | Pitched Pergola | 2023-10-02 | 2023-10-11 | Al | Y | No | No |  | 5.5x2.7 | Appliance white |  |  | Pitched Pergola of deck
Bob Grieve | 021753054 | 118 Woodlands Park Rd, Titirangi | S | 2023-07-27 | Y | Pitched Pergola | 2023-10-11 | 2023-10-17 | D | Y | No | No |  | 4x2.4 | Pioneer Red |  |  | Pitched Pergola of deck
Catherine Eastwood | 0211560602 | 10 Linwood Ave, Mt Albert | S | On Completion | Y | Infill only | 2023-10-16 | 2023-10-19 | D | Y | No | No |  |  | Appliance white |  |  | Infill on side of pergola
Vince Audino | 021 402 011 | 40 Fairmount Dr, Titirangi | B | 2023-08-04 | Y | Gable | 2023-08-04 | 2023-12-20 | D | Y | 16 | No |  |  | Matt Appliance white |  |  | Gable
Richard Pryor | 0212886411 | 47 Sunnyhaven Ave, Beach Haven | J | 2023-08-16 | Y | Pitched | 2023-10-20 | 2023-11-30 | Al | Y | No | 4 |  | 5.9x3.8 | Matt Appliance white |  |  | "Alpaca” from the Shadeview Extreme range for blinds
Garry Ivill | 021494949 | 17 Kesteven Ave, Glendowie | S | On Completion | Y | Infill Gable/Blinds |  | 2023-10-05 | S | Y | No | Yes |  |  | Matt Black |  |  | Gable infill with 2x Omni blinds
Caroline Olagues | 0275445590 | 2/37 Eversleigh Rd, Belmont | S | 2023-08-18 | Y | Pitched | 2023-11-06 | 2023-11-23 | Ali | Y | No | No |  | 3.8x4m | Matt Black |  |  | Pitched Pergola over deck
Fiona Baldwin | 021 718 312 | 3 Cascaden Road, Whangaparaoa | B | 2023-08-21 | Y | Pitched | 2023-10-24 | 2023-12-12 | D | Y | 8 | 3 |  | 6.1x3 | Matt Grey Fiars |  |  | Pitched over patio area away from house with blinds, lights and infills
Kerri Murray | 021871678 | 11 Columbia Rd, Sandringham | J | 2023-08-22 | Y | Pitched Wide Edge | 2023-11-02 | 2023-11-17 | D | Y | No | No |  |  | Matt Black
Louise Crouch | 0273345133 | 432 Clevedon-Kawakawa Rd, Clevedon | S | 2023-08-25 | Y | Invert Pitched x2 | 2023-11-20 | 2023-12-19 | Ali | Y | No | 2 |  | 6x4 | Arctic White |  |  | Inverted pitch on back deck and normal pitch over side deck
David Tippett | 021 913 700 | 37a Faulder Ave, Westmere | J | 2023-08-25 | Y | Pitched Wide Edge | 2023-12-06 | 2023-12-13 | D | Y | No | No |  | 7.5x3 | Matt Black |  |  | Pitched pergola with curved back beam
James Cousins | 0274880081 | 204 Carrington Rd, Mt Albert | S | On Completion | Y | 2x Blinds only |  |  | J,S | Y | No | 2 |  |  | White |  |  | Omni horizontal blind. Ziptrak end blind
Sarah Iles | 021 333 561 | 4 Grut Green, Silverdale | S | 2023-08-25 | Y | Pitched | 2023-11-13 | 2023-11-20 | D | Y | No | Yes |  | 7x5 | Flaxpod |  |  | Pitched pergola over deck. Husband to installl lights?
Louise Taylor | 021620948 | 15 Kawaka Street, Titirangi | S | 2023-09-05 | Y | 2x Pitched | 2023-11-06 | 2024-03-14 | J | Y | No | No |  |  | Matt Black |  |  | 2x Pitched pergolas
Greg Hack | 021 773773 | Middlemore Hospital | S | 2023-09-05 | Y | 2x Ziptrak PVC | 2023-09-25 | 2023-09-28 | S | Y | No | Yes |  |  | White |  |  | 2x Ziptrak PVC blinds in hallway
Eric Culpan | 021 431 229 | 31 Humariri Rd, Pt Chev | S | 2023-09-07 | Y | Inverted Pitch | 2023-11-23 | 2023-12-13 | B&S | Y | 8 | 1 |  | 6.7x2.8 | Matt Flaxpod |  |  | Inverted Pitch with gutter fixed to wall and Lights
Sally Hall | 021720447 | 3 Anda Place, Karaka | S | 2023-09-18 | Y | Inverted Pitch | 2023-11-28 | 2024-02-21 | Ali | Y | No | 1 |  | 3x3m | Matt Flaxpod/Dark Plexi |  |  | Inverted pitch with Ziptrak Blind
Penant & Triumph(Roy) | 0211668866 | 6 Kent St, Newmarket | J | 2023-09-19 | Y | Gable and Blinds | 2023-11-16 | 2023-12-27 | J&J | Y | No | 3 |  | 8.9x4.8 | Matt Flaxpod |  |  | Gable with infilled ends and PVC Ziptrak blinds on 3 sides
Zoe Hunt | 0274208419 | 72 Kauri View Rd, RD4, Papakura | S | 2023-09-21 | Y | Inverted pitched | 2023-12-07 | 2023-10-12 | Ali | Y | No | No |  | 3.7x2.7 | Arctic White |  |  | Inverted Pitch Pergola
Glenda Tilley | 021 02648181 | 20 Exmoor Road, Karaka | B | 2023-09-22 | Y | Pitched Pergola | 2023-12-17 | 2023-12-27 | Ali | Y | No | No |  | 6.2x3 | Matt Grey Friars
Vai - Tongan Church | 02102645711 | 2 Grays Ave, Mangere Bridge | B | 2023-10-19 | Y | Pitched Pergola | 2024-01-15 | 2024-02-20 | J | Y | No | No |  | 11.5x3 | Matt Ghost Grey
Christine Renovation | 0211149943 | 12 King St, Grey Lynn | S | 2023-10-02 | Y | Inverted Pitched | 2023-12-06 | 2023-12-12 | J | Y | 10 | No |  | 6x5 | Matt Black |  |  | Inverted pergola, brackets made on site, Slat wall
Rich Crouch | 021567556 | 26 Carlton Street, Hillsborough | B | 2023-09-22 | Y | Pitched Pergola | 2023-12-18 | 2023-12-29 | J | Y | 4 | No |  | 6x2 | Matt Ironsands
Nadia Herbst | 0223661828 | 73 Pinecrest Dr, Gulf Harbour | B | 2023-09-25 | Y | Pitched Pergola | 2023-12-12 | 2023-12-19 | J | Y | No | No |  | 8x3m | Matt Black |  |  | Pitched Pergola over first floor deck only. No blinds or infill
Fiona Willis | 0212150067 | 9A Summit Dr, Mt Albert | S | On Completion | Y | Blinds only | 2023-10-27 | 2023-11-01 | B,S | Y | No | Yes | [5 empty] | 2x Ziptrak blinds
Alex Fitzgerald | 0212253702 | 8 Wakelin Rd, Beachlands | S | 2023-10-09 | Y | Blinds only | 2023-11-06 |  | S&J | Y | No | Yes |  |  | Matt Black |  |  | 2x ZipTrak blinds with pelmets
Chris Duncan | 0274990435 | 20 Cockle Bay Rd, Cockle Bay | S | 2023-10-11 | Y | Pitched | 2023-12-18 | 2023-12-29 | D | Y | 4 | No |  | 2.6x3.9m | Matt Grey Friars
2024
Blinds to install | [10 empty] | Lights | Blinds
Paul Fewtrell | 0211601113 | 1/14 Brightside Rd, Epsom | S | 2023-10-17 | Y | Pitched | 2024-01-22 | 2024-02-19 | D | Y | Yes | No |  | 7.5x3-5m | Matt Charcoal |  |  | Pitched pergola with opal and dark grey acrylic. Drill out and wire lights only
Alan Krissansen | 0274964346 | 12 Eleanor Pl, Blockhouse Bay | S | 2023-10-10 | Y | Pitched | 2023-01-08 | 2024-01-22 | D | Y | No | No |  | 5.2x3m | Matt Ironsands |  |  | Pitched pergola Over front deck
Graham Rous | 021432747 | 13 Penney Rise, Matakana | B | 2023-10-18 | Y | Gable | 2024-02-20 | 2024-04-03 | D | Y | No | Yes |  |  | Matt Black |  |  | Add $500 to final bill as agreed with owner
Kiwi Rail-Macrennie |  | 12/660 Great South Rd Greenlane Bld 11 | J | On Completion | Y | Pitched canopies | 2024-01-22 | 2024-03-27 | J&S | Y | Yes | No |  |  | Matt Flaxpod |  |  | Building 11: Pathway canopies
Church of Christ NZ |  | Contact: Wayne Houston | S | On Completion | Y | Inside frame & Blind | 2024-03-01 | 2024-04-10 | S | Y | No | Yes |  |  | Matt Ironsands |  |  | Frame of slats over sound equipment desk. Ziptrak bind on front
Katja Makinen | 0220749500 | 71 Shelley Beach Rd, Herne Bay | S | 2023-10-27 | Y | Pitched with fireplace | 2024-03-05 | 2024-03-22 | J | Y | 8 | No |  | 6mx3.9 | Matt Appliance White |  |  | Pitched pergola with fireplace penetration,. 4 legs 100x100mm
Doug Thomson | 021 080 95731 | 3 La Bella Road , Hobsonville | B | 2023-10-30 | Y | Pitched | 2024-04-21 | 2024-04-19 | J | Y | No | No |  | 8x2.6m | Matt Black |  |  | Pitched pergola with acrylic side panels in dark grey tint
Rodney Clough | 0274850059 | 321 Forest Hill Rd, Waiatarua | B | 2023-11-01 | Y | 2x Pitched Pergolas | 2024-02-28 | 2024-03-11 | D |  | No | No |  |  | Matt Charcoal |  |  | 2x Pergolas 3.1 x 5m , 8.8x 1.5m
Steph Ansell | 0211095424 | 26 Jubilee Ave, Onehunga | B | 2023-11-02 | Y | Pitched Pergola | 2024-02-19 | 2024-03-29 | Al | Y | No | No |  | 8x4m | Arctic White |  |  | Upgrade gutter, 4 posts
Colin Brown | 021344997 | 5 Hillside Crs South, Mt Eden | B | 2023-11-13 | Y | Pitched Pergola | 2024-02-27 | 2024-03-07 | J | Y | 6 | No |  | 3.6x4m | Electro Medium Bronze |  |  | See details on svc
Ian Gould | 0274795066 | 39 Wiltshire Place, Howick | B | 2023-11-13 | Y | Inverted Pitch | 2024-02-28 | 2024-03-25 | Al | Y | 12 | 4 |  | 8.2x4.8 | Matt Grey Friars |  |  | Custom brackets and inverted pitch next to pool
TC Tan | 021489303 | 7 Westcoast Rd, Kelston | B | 2023-11-14 | Y | Replace panels | 2024-02-01 | 2024-02-23 | D,B | Y | No | No |  |  | Titania |  |  | Material from Bruces garage - Insulated panel
Sunnie Ko | 02102785206 | 59 Waituarua Dr, Takinini | B | 2023-11-15 |  | Ziptrak blind only | 2023-12-14 | 2023-12-14 | S&J | Y | No | Yes |  |  | Matt Grey Friars Post |  |  | 100x50 post with Ziptrak blind
Ana Corbett | 0211884398 | 152 Seabrook Ave, New Lynn | J | 2023-11-16 | Y | Pitched Pergola | 2024-02-12 | 2024-02-29 | Al | Y | No | No |  | 6.3x3.5 | Matt Appliance White |  |  | Opaque Acrylic
Louise von Sierakowski | 021 870 273 | 2 Esperance Road, Glendowie | B | 2023-11-29 | Y | Pitched Pergola | 2024-03-25 | 2024-05-05 | D | Y | 12 | No |  | 5.6x3.6m | Matt Black |  |  | Pitched Pergola With lights Paid balance of pergola- Just lights to pay in full after installation
Megan Pooley | 02108281912 | 16 Haycock Ave, Mt Roskill | S | 2023-12-03 | Y | Inverted Pitch | 2024-03-18 | 2024-03-22 | D | Y | No | No |  | 3.3x3m | Matt Sandstone Grey |  |  | Inverted pitch with one side infill (Opal)
Sara Negi | 0212335257 | 506 Hillsborough Rd, Lynfield | S | 2024-01-08 | Y | Pitched Pergola | 2024-03-21 | 2024-04-14 | D | Y | 4 | No |  | 4.8x1.5m | Matt Ironsands |  |  | Pitched over first story deck
Derek Phyn | 0212234922 | 13 Plescher Crs, Cambridge | B | 2024-01-10 | Y | Hip and Gable | 2024-03-12 | 2024-04-10 | JW | Y | 12 | No |  | 6.5x4.2 | Matt Black (Clear Arcylic) |  |  | Hip pergola over spa. Gable pergola over patio, Lights in gable only
Rio Bond | 0276126726 | 45 Bell Rd, Beachlands | S | 2024-01-30 | Y | Pitched Pegola | 2024-03-21 | 2024-05-23 | Al | Y | 12 | 4 |  | 6.4x4.6 | Matt Flaxpod (Opal Acrylic) |  |  | Pitched over deck with lights and 4x Ziptrak Blinds
Sally Hall | 021720447 | 3 Anda Place, Karaka | S | On Completion |  | Infill only |  | 2024-02-21 | S | Y |  |  |  |  | Matt Flaxpod |  |  | Side infill panel 2.6 x 700 wide dark grey tint
Andy Scorgie | 021679982 | 2 Meanda Gardens, Pakuranga | J | 2024-02-07 | Y | Gable w/ Infills | 2024-04-03 | 2024-04-18 | J | Y | 12 | No |  | 5.9x5m | Matt Ironsand |  |  | 45degree pitch gable with infills on soffit brackets
Jeff Parkinson | 021 320 207 | 145A Mokoroa Valley Road, Waitakere | B | 2024-02-09 | Y | Pitched Pergola | 2024-03-27 | 2024-04-03 | J | Y | No | No |  | 3.8x3m | Arctic White |  |  | 100x100 posts, Light grey acrylic
Zac Rathbone | 021409178 | 19 Foundries, Freemans Bay | J | 2024-02-20 | Y | Pitched Pergola | 2024-04-04 | 2024-04-12 | D | Y | No | No |  | 6x2.65 | Matt Grey Friars |  |  | Upper deck with 500mm overhang and no gutter
Peter Hutchinson | 0212883601 | 1b The Esplanade, Castor Bay | S | 2024-02-21 | Y | Pitched Pergola | 2024-04-09 | 2024-05-01 | D | Y | 8 | No |  | 7x4m | Matt Ironsands |  |  | First storey deck with overhang and 8 lights
Malcolm Humphries | 027-2922208 | 87 Tiri Road, Matakatia Bay, Whangaparaoa | J | 2024-02-26 | Y | Pitched Pergola | 2023-05-09 | 2024-05-28 | D | Y | No | No |  | 6x2.5 | Matt Flaxpod |  |  | Two pergolas - one cover and one uncovered - small pergola to have no pitch
Nelson Wu | 0212153402 | 4/26 Hayr Road, Three Kings | B | 2024-03-04 | Y | Pitched Pergola | 2024-04-04 | 2024-04-14 | Al | Y | No | No |  | 4m x 3m | Matt Ironsands |  |  | Pitched over patio area.
Greg Drummond | 021948373 | 3 Kaihu St, Northcote | S | 2024-03-08 | Y | Pitched Pergola | 2024-04-22 | 2024-05-01 | J | Y | No | No | 4 | 7.2x2.2m | Matt Appliance White |  |  | Dark Grey Tint
Christine Mann | 0211653515 | 806 Waitakere Rd, Kumeu | B | 2024-02-04 | Y | Pitched Pergola | 2024-04-15 | 2024-04-19 | Al | Y | No | No | 4 | 6.6x1m | Matt Appliance White |  |  | 100x100 posts. Opal Acyrlic
Phillip Borkin | 0277012219 | 16 Rhodes Rd, Mt Albert | J | 2023-03-07 | Y | Pitched Pergola | 2024-05-03 | 2024-05-13 | D | Y | 8 | No | 4 | 4.9x4m | Matt Charcoal |  |  | Standard Pergola
Jonty Kelt | 0277779759 | 18 Paerimu St Orakei | J | 2024-03-13 | Y | Pitched Pergola | 2024-04-23 | 2024-05-17 | D | Y | No | 2 | 5 | 6x4m | Matt Flaxpod |  |  | Box Perimeter
Andy Jones | 0212421060 | 125 Wily Rd, Pukekohe | J | 2024-03-14 | Y | Pitched Pergola | 2024-04-29 | 2024-07-22 | JW | Y | No | 1 | 6 |  | Matt Black |  |  | Roman Blind. Angled back beams
Jemma Nissen | 0212655868 | 15 Taipari Rd, Te Atatu Pen. | J | 2024-03-19 | Y | Gable Pergola | 2024-05-13 | 2024-05-28 | J | Y | No | No | 6 |  | Matt Appliance White |  |  | Gable pergola (Gable all Opal)Pitched pergola with no acrylic.
Wayne Spittal | 021648919 | 861 Whangaparaoa Road, Manly | J | 2024-03-21 | Y | Pergola on roof | 2024-05-31 | 2024-06-08 | D | Y | No | No | 4 | 5.5x3.5 | Matt Sandstone Grey |  |  | Special roof fixing details in client folder. Light Grey tint
David Waddington | 021886798 | 40 Melba Street, Beach Haven(NrthShr) | J | 2024-03-21 | Y | Gable | 2024-05-20 | 2024-06-07 | D | Y | No | No | 5 | 8x3.7m | Matt Appliance White |  |  | Follow end gable from house
Barbara Fountain | 0275215772 | 6 Wimbledon Crs, Glen Innes | S | 2024-03-26 | Y | Pitched Pergola | 2024-04-29 | 2024-05-13 | Ali | Y | No | No | 4 | 6x3m | Arctic White |  |  | Pack out behind back beam
Mike Sweet | 021-667734 | 26 Rossgrove Trc, Mt Albert | B | 2024-03-27 | Y | Pitched Pergola | 2024-05-08 | 2024-05-28 | Ali | Y | No | No | 3 | 3mx3m | Matt Appliance White |  |  | Between house and sleep out- No posts
Phillipa Robinson | 0272729951 | 45 Birch Rd, Karaka 2580 | B | 2024-04-16 | Y | Reroof conseratory | 2024-05-30 | 2024-06-11 | S/J | Y | No | No | 2 | 4.6x2m | Matt Black |  |  | Remove existing conservatory roof and replace with 50x50 frame and acrylic
Donn de Silva | 021 86 88 44 | 2 Oakford Park Crescent, Greenhithe | B | 2024-04-17 | Stk | Pitched Hip Pergola | 2024-07-04 | 2024-08-19 | D | Y | No | No | 8 | 8.5x4m | Matt Black |  |  | Remove existing pergola. (86m2) with only 30m2 of covered area the rest decorative only.
Colin Brown | 021 344 997 | 5 Hillside Crs South, Mt Eden | B | 2024-04-17 | Y | Small Pitched Pergola | 2024-08-08 | 2024-08-13 | JW | Y | No | No | 3 | 1.7x1.4m | Electro Medium Bronze |  |  | Small pitched Pergola, 100x100 post, Side panel
Mark Elliott (WRNZ) | 0274046156 | 8 Brown St, Little Manly | B | 2024-04-17 | n/a | Uninstall/reinstall | 2024-04-22 | 2024-06-14 | S/J | Y | No | No | 2 | N/A | N/A |  |  | Dismantle pergola ready for reroof. Reinstall pergola. Insurance
Shayne Wijohn | 0210788920 | 57 Siren St, Milldale (Silverdale) | B | 2024-04-19 | Stk | Gable/Pitched | 2024-06-13 | 2024-07-09 | D | J | 12 | No | 7 | 7x2.8 | Black- Stock |  |  | Gable from end of house. Joined to pitched down side of house
Eva | 0276162288 | 87 Joshua Carder Dr, Hobsonville | S | 2024-04-22 | Y | Pitched Pergola | 2024-06-06 |  | D |  | 12 | 4 | 5 | 5.4x4.3 | Matt Grey Friars |  |  | Pitched pergola with blinds, lights and solid infill.
Petar & Debbie Kust | 021412912 Pet | 88 Muriwai Rd, Muriwai | B | 2024-04-29 | Y | Double Hip Pergola | 2024-09-02 | 2024-10-25 | JW | Y | 18 | 5 | 7 | 8.8x5m | Matt Flaxpod |  |  | Double Hip Pergola - Confirm lights prior to job.
Glenn Bratton | 0274581600 | 50 Hiwihau Pl, Glenfield | B | 2024-05-01 | Y | Gable | 2024-07-23 | 2024-04-09 | D | Y | No | No | 6 | 5.7x3m | Matt Appliance White |  |  | Extend out gable to match house roof (Light grey tint) Decorative gable end
Kohimarama School | 02102062931 | 112 Kohimarama Rd, Kohimarama | S | on completion | Y | Replace w Acrylic | 2024-07-09 | 2024-08-01 | S&J | Y | No | No | 2 |  | Opal Acrylic |  |  | Replace storm damaged twinwall with acrylic (Needs new Rubbers) Russel Graham-Property Manager
Manukau Motor Lodge | 0274732487Ron | 631 Great South Rd, Manukau | S | on completion |  | Gable | 2024-05-21 | 2024-06-04 | S/J | Y | No | No | 5 | 7x8m | Matt Black |  |  | Replacing glazed roof over Motel entry area. Work in with builder (100x100 gutters)
Greg Ross-Gordon | 0272982648 | 25 Evans Court, Pukekohe | B | 2024-02-13 | Y | Horizontal Blind | 2024-04-03 | 2024-04-26 | S/J | Y | No | 1 | [5 empty] | Omni horizontal blind.
Robbie Butterworth | 021 158 7039 | 37D William Potter Lane, Karaka | S | 2024-05-09 | Y | Pitched pergola | 2024-08-21 | 2024-08-26 | JI | Y | No | No | 3 | 4.2x1.8 | Matt Black |  |  | No legs. Attached to weatherboard and existing post.
Clever Construction | 02102681804 | 35 Catherine McLean Rd, Pukekohe | S | 2024-05-14 |  | Pitched Pergola | 2024-07-02 | 2024-07-09 | S&J | Y | No | No | 4 |  | Matt Ironsands |  |  | Pitched pergola with extra legs for aluminium joinery
Phillip Borkin | 0277012219 | 16 Rhodes Rd, Mt Albert | B | On Completion |  | Extension | 2024-05-16 | 2024-05-27 | D | Y | No | No | 1 | 6m x0.6m | Matt Charcoal |  |  | Extend existing pergola
Tamy Rosa | 0275175252 | 1 Kiokio Pl, Swanson | S | 2024-05-16 | Stk | Gable and pitched | 2024-07-29 | 2024-08-09 | J&J | Y | No | No | 5 |  | Matt Black |  |  | No Lights
Andy McCowan | 021582112 | 53 Tindalls Bay Road, Whangaparoa | J | 2024-05-17 | Y | Mixed, Panels | 2024-11-26 | 2025-07-19 | JW | Y | Yes | 2 |  |  | Matt Gull Grey | 6m Grey - 8 sheets |  | Building Consent- Payment received 19/12/24
Rodney Clough | 0274850059 | 321 Forest Hill Rd, Waiatarua | S | 2024-05-18 | Y | Pitched | 2024-08-21 |  | D | Y | No | No | 5 |  | Matt Charcoal |  |  | Pitched pergola over first floor deck area
Adelle Edmunds | 0211068802 | 10 Drysdale Pl, Howick | S | 2024-05-20 | Y | 2x Pitched | 2024-07-23 | 2024-08-21 | J&J | Y | 6 | No | 5 | 7.4x3m | Matt Titania |  |  | Entry Pergola (Lignite)/ Pitched pergola over rear deck (Titania) (White Lights)
Josh Lawrence | 0220295217 | 37 Seaview Trc, Mt Albert | S | 2024-05-27 | Stk | Pitched | 2024-08-06 | 2024-08-16 | Kris | Y | No | No | 4 | 5x2.8 | Appliance White |  |  | Pitched over ground level deck area- attach to fascia
Raymond Meade | 0274807513 | 71 Puketutu Rd, Bombay | S | 2024-05-28 | Stk | Pitched | 2024-08-12 | 2024-08-21 | Ali | Y | No | 1 | 4 | 9x3m | Matt Black |  |  | Pitched pergola over deck with Ziptrak and infill on one end
Ben d'Anvers | 022 021 0414 | 27 Smale Street, Point Chevalier | B | 2024-06-06 | Y | Gable | 2024-08-01 | 2024-08-27 | D | Y | No | 3 | 10 | 5x4.3m | Appliance White |  |  | Gable with box perimetre
John Whyman | 021747034 | 14 Gunner Dr, Te Atatu Pen | S | 2024-06-07 | Y | Pitched | 2024-08-14 | 2024-08-20 | JW | Y | Yes | No | 4 | 4.7x4m | Matt Titania |  |  | Pitched Pergola- Drill and wire for lights only
Sujatha Rani | 021 0222 2277 | 54 Turnberry Dr, Wattle Downs | B | 2024-06-08 | Y | Pitched | 2024-08-12 | 2024-08-21 | JI | Y | No | No |  | 7.1x3m | Matt Ironsands |  |  | Pitched Pergola over patio. Infill against house (3x blinds on hold)
Pierre Houzet | 02108368318 | 2A Heathcote Rd, Castor Bay | B | 2024-07-02 | Stk | Hip Pergola | 2024-08-19 | 2024-08-30 | JW | Y | No | No |  | 7.3x2.5 | Matt Black |  |  | Hip and pitched pergola
Robert Waddell | 0274885744 | 55 Waitea Rd, Muriwai | B | 2024-07-05 | Stk | Gable Carport | 2024-09-03 | 2024-09-17 | D | Y | No | No |  | 6.3x5.5 | Matt Black |  |  | 150x150 posts 30degree pitch
Ryan Hay | 021 237 6168. | 8 Upper Queen Street, Auckland CBD. | B | 2024-07-17 | Y | Gable infill & blinds | 2024-08-27 | 17/07024 | JI&S | Y | No | 2 |  |  | Matt Ironsands |  |  | Gable infill (clear acrylic) and framing with 2x Ziptrak PVC blinds
Ann-Mariee Evans | 0210630340 | 99 Athenree Rd, Athenree (Waihi) | B | 2024-07-18 | Stk | 4 Hips over louvers | 2024-10-21 | 2024-10-29 | JW | Y | No | No |  |  | Appliance White |  |  | Roof over louverd conservatory . (Plexi)
Mel Bell | 021 210 9035 | 20a Reidy Pl, Pukekohe | S | 2024-07-26 | Stk | Gable | 2024-09-18 | 2024-10-21 | DH | Y | Yes | 5 | 6 |  | Matt Black |  |  | Gable to extend from front of house with gable infill and blinds
Naina Parma | 021 108 9316 | 14a Eleanor Pl, Blockhouse Bay | B | 2024-08-11 | Y | Blinds | 2024-09-17 | 2024-10-22 | JI |  | No | 4 |  |  | Matt Grey Friars |  |  | Side triangular infills and extra posts. Supply and install 4x Ziptrak blinds
Megan Biddles | 021 460 646 | 70 Macky Rd, Kaukapakapa | B | 2024-08-11 | Y | Inverted Pitched | 2024-09-18 | 2024-10-09 | JW | Y | 14 | No | 5 | 10x3.5 | Matt Flaxpod |  |  | 100x100 post connected to deck. Lights to be confirmed. Soffit brackets
Lynn Parkes | 027 268 9677 | 9/54 Lakeside Dr, Orewa | B | 2024-08-15 | Y | Pitched | 2024-09-25 | 2024-10-07 | JW | Y | No | No | 4 |  | Silver Pearl |  |  | Blinds payment 12-12-24
Brad- Lateral Homes | 021 438 660 | 124 Weatherly Rd, Torbay | B | 2024-08-15 | Stk | Inverted Pitched | 2024-10-16 | 2024-12-12 | DH | Y | No | 1 | 4 | 6x3.6m | Appliance White |  |  | 100x100 posts connected to deck. Soffit brackets Ziptrak Bilnd
Rich Ferretti | 0220 442 811 | 37 Bob Charles Dr, Golflands | B | 2024-08-19 | Y | Pitched | 2024-11-01 | 2024-11-14 | Ali | Y | no | no |  | 11.7x2.5 | Matt Ghost Grey |  |  | 100x100 posts connected to concrete. Soffit brackets
Allison Bailie | 021392467 | 84 Harvest Ave Orewa | B | 2024-08-25 | Stk | Pitched | 2024-10-01 | 2024-10-18 | JW | Y | No | No | 6 | 7.5x4m | Matt Black |  |  | 100x100 posts
Awhitu Fire Station | 0274992209 | 2678 Awhitu Road, Awhitu | S | On Completion | Y | Freestanding Pitch | 2024-09-26 | 2024-10-07 | S&JI | Y | No | No | 1 | 1.8x2m | Matt Titania |  |  | 4x 100x100 posts connected to concrete
Lindy Johnson | 0274511033 | 26a Tizard Rd, Birkenhead | B | 2024-08-30 | Stk | Pitched | 2024-09-26 | 2024-10-09 | DH | Y | No | No |  | 6.5x5m | Matt Black |  |  | 100x100 posts (Twisted frame?)
Andy Jones | 0212421060 | 125 Wily Rd, Pukekohe | S | On Completion | Y | Shade Sail | 2024-09-26 | 2024-10-01 | S&JI | Y | No | No | 1 | N/A | N/A |  |  | Shade sail installed onto pergola - Shade Systems
Stephen Whiteside | 021774234 | 34 Sherbourne Road, Mt Eden | B | 2024-09-02 | Stk | Gable | 2024-10-08 |  | DH | Y | No | No |  | 3.8x2.8m | Appliance White |  |  | Gable 25 degree- existing timber side beams
Natalie Innes | 0223285843 | 322 Birdwood Road, Massey | B | 2024-09-02 | Stk | Pitched | 2024-10-08 | 2024-10-15 | JW | Y | No | No |  | 5.8mx4m | Matt Black |  |  | 100x100 posts. Modular. Acrylic Light Grey
Haley Judson | 0279367722 | 12 Lester St, Hobsonville | B | 2024-09-03 | Stk | Pitched | 2024-09-30 | 2024-10-07 | JI | Y | No | No |  | 3.9x3m | Matt Black |  |  | 1 post attached to concrete 100x100
Karoline Marshall | 0274795396 | 15 Smale Street, Pt Chev | B | 2024-09-03 | Stk | Pitched | 2024-10-11 | 2024-11-14 | Ali | Y | No | No |  | 6.9x3.5m | Appliance White |  |  | 100x100 posts attached to deck. Brackets
Roy Cross | 021 270 3231 | 109 Brighton Road, Parnell. | S | 2024-09-04 | Stk | Gable | 2024-11-12 | 2024-12-03 | DH | Y | 10 | No |  |  | Metro Silver Pearl Kinetic
Jo Williams | 027 274 4708 | 11a Kakariki Ave, Mt Eden | S | 2024-09-07 | Y | Parallel Gable | 2024-10-24 | 2024-11-15 | DH | Y | 8 | No | 6 |  | Silver Pearl Kinetic |  |  | Soffit Brackets. DP under deck
Colin Brown | 021 344 997 | 5 Hillside Crs South, Mt Eden | S | On Completion | Y | Infill and blind | 2024-10-31 | 2024-12-05 | JW | Y | No | 2 | 1 |  | Electro Medium Bronze |  |  | Triangular infill on upper deck with legs for Ziptrak Blind
Caroline von Sierakowski | 021 830221 | 11a Esperance Rd, Glendowie | B | 2024-09-12 | Stk | Inverted Pitched | 2024-11-26 | 2024-12-11 | Ali | Y | 12 | No | 5 |  | Matt Black |  |  | Garage Pergola only at this stage. Brackets to front of garage. Side infill next to house
Linda Nelson | 0274772702 | Ranfurly Care - 56 Ranfurly Road Epsom. | S | 2024-09-12 | Stk | Wave Shade x2 | 2024-10-03 | 2024-10-15 | JI |  | No | No | 1 |  | Appliance White |  |  | Install 150x50 beams with 2x WaveShades
Miranda Wagg | 021990470 | 94 Hepburn St, Freemans Bay | S | 2024-09-20 | Stk | 2x Pitched | 2024-10-29 | 2024-12-10 | KB | Y | 10 | 1 | 5 |  | Matt Black |  |  | Rear Patio pergola with lights and blind. Front entry pergola with lights
Ed Aitken | 0275800294 | 119 Kennedy Rd, Diary Flat | B | 2024-09-13 | Y | Pitched and gable | 2024-11-26 | 2025-08-18 | DH | Y | Yes | No | 10 |  | Matt Black
Lee Smith | 027 3550 340 | 167B Blackbridge Rd, Dairy Flat | S | 2024-09-20 | Stk | Pitched | 2024-10-10 | 2024-10-25 | DH | Y | No | No | 4 | 7.4x3m | Matt Black |  |  | Pitched pergola with soffit brackets
Ross Fulton | 021476360 | 239 Titirangi Road, Titirangi | S | 2024-09-23 | Stk | Inverted Pitched | 2024-11-11 | 2024-12-19 | JI | Y | No | 4 | 6 |  | Appliance White |  |  | Inverted over deck. Blinds, vert panels and infills (End infill Opal)
Chris Baker | 021724990 | 15 Bardsey St, Glendowie | B | 2024-09-23 | Y | Gable/ThermPanels | 2024-11-11 | 2014-12-23 | JW |  | 16 | 4 | 8 |  | Appliance White |  |  | Gable with insulated panels and acrylic sheets Final payment made 9-03-25
David Geary | 0220 314 946 | 11 Alma Rd, Milford | B | 2024-09-27 | Y | Pitched | 2024-12-16 | 2024-12-21 | Ali | Y | No | No |  | 5mx4m | Matt Ironsands |  |  | Pitched pergola over deck. White Soffit brackets. Half painted ironsands
Rose Thodey | 021 762 765 | 8/63 Vermont St, Ponsonby | S | 2024-09-27 | Y | Pitched | 2024-11-01 | 2024-12-02 | JW | Y | No | 1 |  | 5.4x3.3m | Matt Titania |  |  | Pitched Pergola on 4 legs (100x100)
Gerrit Le Grange | 0210463935 | 107 Braemar Rd, Castor Bay | B | 2024-10-01 | Stk | Pitched | 2024-11-06 | 2024-11-13 | DH | y | No | No |  | 9 x 2.7m | Matt Black |  |  | Upper deck area. Modular. Plexi 14 panels - 5 sheets
Roger Murray | 027 294 7811 | 37 Harbour View Rd, Pt Chevalier | B | 2024-10-03 | Y | Pitched | 2024-11-13 | 2024-11-26 | Ali | Y | No | No |  | 5.2x4.8m | Matt Irondsands |  |  | Modular 8 panels full size. White Soffit brackets. Half painted ironsands (Light Grey Crystalite)
Trish Freeman | 0274430837 | 79 Park Rd, Titirangi | S | 2024-10-11 | Y | Pitched | 2024-12-09 | 2024-12-17 | Ali | Y | No | No |  | 3.4x6m | Matt Ironsands |  |  | Pitched pergola over deck. Start under gutter.
Terry Lawrence | 0272164480 | 43 Bannings Way, Hobsonville | B | 2024-10-13 | Y | Infill and blind | 2024-12-09 | 2025-02-24 | JI | Y | No | 1 |  |  | Matt Grey Friars |  |  | Infill, vertical panels, Ziptrak into existing pergola. Light Grey Acrylic
Linda Nelson | 0274772702 | Ranfurly Care - 56 Ranfurly Road Epsom. | S | 2024-10-17 | Y | Wave Shade | 2024-11-22 | 2024-11-28 | JI | Y | No | No |  |  | N/A |  |  | Third WaveShade over patio area
Allison Bailie | 021392467 | 84 Harvest Ave Orewa | S | 2024-10-22 | Y | Infill and blind | Ready to go | 2024-12-02 | JI | Y | No | 1 |  |  | Matt Black |  |  | Triangular infill with one leg for Ziptrak Blind
C3 Interiors - Jessa | 022 029 4746 | Auckland Airport- Int Departure Termin | S | 2024-11-11 | Y | Ziptrak Blinds | 2024-11-27 | 2024-12-27 | S&J | Y | No | 4 |  |  | N/A |  |  | 4x Ziptrak blinds with removable posts in the middle of each
Naina Parma | 021 108 9316 | 14a Eleanor Pl, Blockhouse Bay | S | 2024-10-31 | Y | Infill and blinds | Ready to go | 2025-03-30 | JW | Y | no | 4 |  |  | Matt Grey Friars
Thelma Meyer | 0210429932 | 12/32 Dudley Rd, Mission Bay | S | 2024-11-04 | Y | WaveShade | Ready to go | 2024-12-06 | S&J | Y | No | No |  |  | N/A |  |  | WaveShade into existing timber frame
Stephen Whiteside | 021774234 | 34 Sherbourne Road, Mt Eden | S | On Completion |  | Gable infill | 2024-11-06 | 2024-11-29 | JI | Y | No | No |  | 3mx0.4m | Appliance White |  |  | Plexi
2025
Aaron Young | 021747470 | 2 Manurere Ave, Takapuna | S | 2024-04-08 | Y | Freestanding Pitched | 2025-01-06 | 2024-01-13 | DH |  | No | No | 4 | 5x3m | Matt Flaxpod |  |  | Short Timber posts for legs to drop over are installed by landscapers
Elaine Colman | 021621943 | 3 Kiokio Pl, Swanson | S | 2024-10-04 | Stk | Pitched | 2025-01-06 | 2025-02-28 | JI | Y | 5 | 4 |  | 6.5x2.4m | Matt Black |  |  | elainerc@xtra.co.nz Closed in room with blinds
Dardie Kelso | 021 331 110 | 61 Selborne Rd, Grey Lynn | S | 2024-10-07 |  | Pitched | 2025-02-03 | 2025-02-12 | JW | Y | No | No |  | 5.8mx4m | Matt Ironsands |  |  | Possible wiringing for fan. 1x 100x100mm post
Martin Baylis | 021871993 | 2/11 Tuperiri Rd, Epsom | S | 2023-11-20 | Y | Pitched Pergola | On hold | 2025-11-07 | JI | Y | 12 | No |  | 4.9 x5.6m | Matt Flaxpod | Crystalite 8x 6m |  | Pitched Pergola over Patio. Post brackets to be attached soon (On hold due to consent issues)
David Read | 0274 985 524 | 10 Jury lane, Pauanui, Coromandel peninsula. | B | 2024-10-02 | Y | Pitched | 2025-01-27 | 2025-03-25 | JW | Y | No | 2 |  | 6.5x3.7m | Matt Ironsands |  |  | Clear infills. Clear PVC blinds (extra 200x50 for blinds)
Ollie Fraser (Fraser Brothers) | 0276727616 | 3 Tamaki Dr, Auckland | S | 2024-09-02 | y | Large Pitched | 2025-06-23 | 2025-07-30 | JW | Y | ? | y |  |  | Matt Navy | 6m Grey - 20 sheets |  | Balance of deposit paid 7/03/25 - Blind part payment 5/12/25
Tony Oldham | 021 853 189 | 2/27 Vine St, St Marys Bay | B | 2024-10-25 | Stk | Pitched | 2025-01-13 |  | JW |  | no | no |  | 5.1x4m | Matt Black |  |  | Pitched 5degrees Twisted
Richard Mandeno | 0274396652 | 16C Maunganui Road, Birkenhead | B | 2024-10-30 | Y | Pitched | Ready to go | 2025-01-30 | JW | Y | No | No |  |  | Matt Flaxpod |  |  | Stingray Pergola 2.9m x 2.3m
Debbie Dun | 0212466996 | 216 Atkinson Rd, Titirangi | B | 2024-11-04 | Stk | Inverted Pergola | 2025-02-04 | 2025-02-14 | DH | Y | No | No |  | 3.9x3m | Matt Black |  |  | 2x Pergolas
Ross Collett | 021 277 3366 | 12 Eclipse Pl, Half Moon Bay | B | 2024-11-07 | Stk | 2x Pergolas | 2025-02-03 | 2025-02-26 | Ali | Y | 12 | 2 |  |  | Matt Black |  |  | Upper deck and carport pergola
Andy Roberts | 021585987 | 23 Neville St, Pt Chev | B | 2024-11-13 | Stk | Pitched Pergola | 2025-02-11 | 2025-03-03 | DH | Y | No | No |  | 7m x 4m | Appliance White |  |  | 15 degree pitch (No Opal) Remove lights
Dan Teeboon | 021 708 180 | 96b Balmain Rd, Chatswood, Birkenhead | B | 2024-11-19 |  | Pitched Pergola | 2025-03-03 | 2025-03-13 | DH |  | No | No |  | 6.3x1.5 | Appliance White
Rob Deed | 021 270 4020 | 29B Kenmure Ave, Forrest Hill | B | 2024-11-20 |  | Gable Pergola | 2025-02-17 | 2025-03-19 | DH | Y | No | No |  | 6.7x3.5 | Matt Black |  |  | Follow 20 degree gable from house
Larissa Flavell | 0212869516 | 14 Paykel Avenue, Farm Cove | B | 2024-11-26 |  | Gable Pergola | 2025-02-25 |  | Ali |  | 16 | 3 |  | 5.5x5.35 | Matt Flaxpod |  |  | 15 degree pitch (light Grey)
Zones Landscapes | Kate 021303314 | 67b Asquith Ave, Mt Albert | J | 2024-11-27 |  | Pitched Welded | 2025-01-21 | 2025-03-17 | JW | Y | No | No |  |  | Matt Black
Zones Landscapes | Kate 021303314 | 167a Pt Chevalier Rd | J | 2024-11-27 |  | 2x Pitched Pergolas | 2025-03-05 | 2025-04-15 | JW | Y | No | no |  |  | Black | PSP Blue Breeze |  | 750mm wide x 8mm thick Polycarb roofing with PSP joiners
Steve Jenkins | 021 947 920 | 45b Harbour View Rd, Pt Chevalier | S | 2024-12-01 | Stk | Pitched Pergola | 2025-03-17 | 2025-03-26 | JW | Y | No | TBC |  | 6m x 3m | Matt Black |  |  | Remove existing timber pergola. Charge for tipping only. Possible blind and infill on end
Mark Scowen | 021 2468 367 | 46 Kumukumu Rd, Long Bay | B | 2024-12-01 |  | Pitched Pergola | 2025-02-13 | 2025-02-19 | JW | Y | No | No |  |  | Matt Black
Juliet Fleischl | 021 264 3165 | 45i Habour View Rd, Pt Chev | S | 2024-12-02 | Stk | Pitched Pergola | 2025-02-26 | 2025-04-10 | JW | Y | No | No |  |  | Appliance White TBC |  |  | Remove existing pergola. New wider pergola
Steven Young | 021 258 3432 | 12/2 Rarangi Rd, St Heliers | S | 2024-12-04 |  | Acrylic and gutter only | 2025-02-03 | 2025-04-02 | S&J | Y | No | No |  |  | Black |  |  | 10mm grey Plexi sheets with joiners onto existing timber pergola
Helen Reinen | 021 262 6492 | 4 Motutapu Ave, Manly | B | 2024-12-06 |  | Pitched Pergola | 2025-02-26 | 2025-03-21 | DH | Y | No | No |  |  | New Denim Blue
Karoline Marshall | 0274795396 | 15 Smale Street, Pt Chev | S | 2024-12-13 |  | Infills and blinds | 2025-02-18 | 2025-03-23 | JW | Y | No | 2 |  |  | Appliance White |  |  | Vertical panel, 2x PVC Clear Blinds, Triangular infill
Kathryn Randall | 0210749208 | 4 Mappin Place, Chatswood | B | 2024-12-17 | Y | Pitched Pergola | On hold |  |  |  | No | No |  |  | Sliver Star Kinetic | Clear TBC |  | Job on hold at this stage
Summerland School | 021 544 480 | 62 Summerland Dr, Henderson | B | 2025-02-18 | Stk | Pitched Pergola | 2025-02-24 | 2025-02-28 | JI | Y | No | No |  |  | Black |  |  | Blair Giles (Co-Principal) Light grey sheets
Ralph Dias | 021908752 | 29 New Windsor Rd, Avondale | B | 2024-12-30 |  | Gable | 2025-03-06 | 2025-03-21 | DH | Y | No | No |  | 4.5x4m | Black (Confirm) |  |  | Gable with infills
Chris Holland | 0211794634 | 2 Violet St, Mt Albert | B | 2025-01-01 |  | Pitched Pergola | 2025-03-13 | 2025-05-01 | DH | Y | No | No | 3 | 4x2m | Matt Grey Friars |  |  | Smallest option priced. 4mx2m
Chaney Construction | 0274446110 | 10 Birkenhead Ave, Northcote | J | 2024-11-25 |  | Commercial Pitched |  |  |  |  | No | No | 12 |  | Silver Annodised TBC
Ksenija Chobanovich | 027 203 2555 | 22 Crocombe Crescent, Beach Haven | B | 2025-01-20 |  | Gable | 2025-03-24 | 2025-04-27 | DH | Y | No | 1 | 5 | 5.2x4m | Appliance White |  |  | Gable over deck area
Vish Dayal | 021 921 983 | 731E Remuera Rd, Auckland | J | 2025-01-21 | y | Pitched | 2025-03-10 | 2025-05-30 | Ali | Y | NO | 2 | 4 | 5.8x3.1m | Ironsand |  |  | Paid for lighting but no longer go for it - take it out of final invoice
Camila Gallo | 0211955881 | 241b Rangatira Road, Beach Haven | B | 2025-01-22 |  | Gable | 2025-03-18 | 2025-04-02 | DH | Y | No | No |  | 6.2x3.5 | Black
Jamie France | 021 909 987 | 20 Sudeley St, Orakei | S |  |  | WaveShades | 2025-05-01 | 2025-05-06 | S&E | Y | [7 empty] | 3x WaveShades
Tom Herring | Tom 021 190 2403. Vicky 021 960 834. | 5 James Evans Drive, Northcote. | B | 2025-02-04 |  | Pitched | 2025-04-01 | 2025-04-15 | DH | Y | No | No |  | 9.3x2.1m | Appliance White |  |  | Pitched pergola. No blinds at this stage
Chris Gibb | 0211331919 | 216 Riddell Rd, Glendowie | B,S | 2025-03-06 | y | Pitched | 2025-05-01 | 2025-06-02 | JW | Y | 10 | No |  | 6x5m | Matt Black | 5m Grey - 10 sheets
Emily King | 0278130000 | 24 Lannan Road, Waiheke | J | 2025-02-14 |  | Double Gable | 2025-04-28 | 2025-05-26 | JW | Y | No | No |  | 8x2.5 | Appliance White | Opal 4x5m, 4x4m |  | Michelle- designer 021 280 1101
Guenter Urbanski | 021 984 281 | 9 Vinistra Rd, Huapai | B | 2025-02-07 |  | Valley Pergola | 2025-04-28 | 2025-05-08 | DH | Y | No | No |  | 4.7&3.2x1.5 | Matt Titania | Dark Plexi |  | Beam to continue through to house
Rob Ebert | 021 487 752 | 3 Makete Cresent Hobsonville | B | 2025-02-09 |  | Pitched Pergola | 2025-03-28 | 2025-04-03 | JW | Y | No | No |  | 5.6x3.5m | Black | 4m Grey - 9 sheets
Stuart Jones | 021497682 | 12 Clydesdale Ave, Somerville, Howick | B | 2025-02-09 |  | Pitched Pergola | 2025-03-17 | 2025-04-03 | Ali | Y | No | No |  | 7x4.5m | Appliance White | Opal
Hilary Lill | 021910750 | 17 Roseneath Place, Birkdale | B | 2025-02-12 |  | Pitched Pergola | 2025-04-16 | 2025-05-19 | DH | Y | No | 2 |  | 7.2x3m | Appliance White | Plexi Lgrey x4 |  | Only one pergola- not the entry one at this point Final Blind payment 18/06/25
Leanne Freeman | 027 276 7061 | 11 Sadgrove Trc, Mt Albert | S | 2025-02-28 |  | Pitched Pergola | 2025-04-23 | 2025-05-07 | JW | Y | No | No |  | 2m x1.5 | Appliance White | Plexi Lgrey x1 |  | Small pergola over upper deck area. Special bracket for leg.
Linda & Gavin Rugg | 021588646 | 17 Hawaiian Parade, Arkles Bay | B | 2025-03-04 |  | Pitched Pergola | 2025-05-06 | 2025-06-06 | DH | Y | No | 2 |  | 8.1x2.1 | Appliance White | Plexi Lgrey x3 plus 1 bay |  | Steel beam across front
Helen Wanstall | 02102474496 | 711 Huia Rd, Parau 0604 | B | 2025-03-10 |  | Gable | 2025-05-13 | 2025-05-26 | DH |  | No | No |  | 5.8x4.5 | Matt Black | Plexi Lgrey 4.5 sheets |  | 150x150 posts 20 degree pitch 2x deposits. 10-3-25 and 17-3-25
Penny Gillies | 021 146 7006 | 254 St Andrew's Rd, Epsom | J | 2025-03-15 |  | Pitched Pergola | 2025-03-31 | 2025-04-16 | Ali | Y | No | No |  | 5x4m | Appliance White | 4m- Grey |  | Brackets and high back beam to match side roof.
Bo Henry | 0211600179 | 28 Wicklow Rd, Narrowneck | S | 2025-03-17 |  | Inverted Pitched | 2025-04-10 | 2025-05-26 | DH | Y | No | 3 |  | 4.9x 3m | Black | Plexi Lgrey TBC |  | Rear Deck Pergola. Inverted over deck. Blinds and infills
Vivian Rusman | 021 2834 747 | 24 Banks Drive, Aongatete, Bay of Plenty | B | 2025-03-17 |  | Gable | 2025-06-04 | 2025-06-27 | B&E | Y | No | No |  |  | Black | 4m and 5m Grey
Sandie Naylor | 0211491580 | Site: 1a Forbes St, Onehunga | S | 2025-03-19 |  | Pitched Pergola | 2026-02-23 |  | DH |  | Yes | No |  |  | Appliance White | 4x Plexi Clear |  | Now wants lights
Shawn Lewis | 021 989 146 | 12 Jellicoe Rd, Murrays Bay | B | 2025-03-23 |  | Gable | 2025-05-29 | 2025-07-01 | DH | Y | No | No |  | 7.6x3.7m | Appliance White | Plexi Lgrey 6 sheets |  | Parallel gable - wiring for fan and lights Gable infills final payment 19-08-25
Marc Humphries | 027 478 2717 | 5 Cross St, Manly, Whangaparoa | B | 2025-03-24 | y | Pitch Pergola | 2025-05-20 | 2025-06-13 | DH | Y | No | No |  | 6.6x3.6 | Matt Titania | 4m- Grey - 11 sheets
Dan Johnson | 0211599130 | 47 English Oak Drive, Schnapper Rock | B | 2025-03-26 |  | Gable | 2025-06-12 | 2025-06-29 | DH | Y | 12 | No |  | 6m x 5m | Appliance White | Plexi Dark Grey
Kit and Noriko Hickey | 021 969 472 | 73 Pupuke Rd, Northcote | S | 2025-03-25 | y | Inverted Pitched | 2025-10-06 |  | JW |  | No | No |  |  | Appliance White | Opal |  | Entry pergola with slat side wall and hand rail
Richard Michael | 022 650 9426 | 207 Carter Rd, Oratia | B | 31/04/2025 |  | Inverted Pitched | 2025-05-20 | 2025-06-09 | JI | Y | No | No |  | 6.7x3m | Black | Plexi - Lgrey - 4 sheets |  | 3 posts Inverted Pergola
Scott Fichett | 021 735 528 | 55 Korora Rd, Waiheke Island | B | 2025-04-04 |  | Gable | 2025-05-05 | 2025-05-19 | JW | Y | No | No |  | 5.3x3.9 | Black | Plexi - Lgrey - 4 sheets |  | Box perimetre with gable inside on brackets
Denys Coote | 027 667 3024 | 32 Worsnop Way, Silverdale | B | 2025-04-11 |  | Gable and Pitched | 2025-07-01 | 2025-07-15 | DH | Y | No | No |  |  | Black | 4m- Grey - 12 sheets |  | Wire for lights only
Josy Campbell |  | 48a Wilson Rd, Warkworth | J | 2025-04-24 | y | Gable | 2025-08-14 | 2025-10-24 | JW | Y | Y | 2 |  |  | Black |  |  | Project Manager - Aliesha Stent 021 216 7353
Sharon Turner | 0212492255 | 26 Summit Dr, Mt Albert | B | 2025-04-30 |  | Pitched | 14/05/025 | 2025-04-30 | JI | Y | No | No |  | 2.6 x 1m | Appliance White | Plexi Lgrey |  | Extend existing veranda roof
Clegg Builders | 021 962 072 | 32 Lauren Grove, Ardmore | S | 2025-05-02 |  | Pitched | 2025-05-29 | 13/06/285 | JW | Y | 8 | No |  | 5 x 3.4m | Black | Plexi- Grey - 4 sheets |  | Mudroom- Pitched pergola with CLEAR vertical panel section.
Kate Walker | 027 317 5511 | 201 Muriwai Valley Rd, Waimauku | B | 2025-05-04 |  | Pitched | 2025-07-08 | 2025-07-14 | DH | Y | No | No |  | 5.8 x5m | Appliance White | 5m-Grey - 9 sheets
Shelley Dunlop | 021 234 2094 | 32 Churchouse Rd, Greenhithe | B | 2025-05-16 | y | Freestanding Pitched | 2025-07-14 | 2025-10-02 | DH | Y | No | 2 |  | 3.5x3.2m | Ironsands | Plexi - Lgrey |  | Owner- Shelley 021 234 2094 (Dunlop Family Trust) Jesse installs blinds 25/09/25
Tim Hill | 027 315 7198 | 2/20 Steen Pl, Mangere Bridge | S | 2025-05-18 |  | Pitched Pergola | 2025-06-18 | 2025-06-26 | ES,JI |  | No | 2 |  | 5mx3m | Appliance White | Plexi - CLEAR - 3 sheets |  | 2x Omni Blinds (Urban Marble) Blinds final payment 24/07/25
Lindesay Construction | 021 744 180 | 16 Te Ara Oneone, Te Arai | J | 2025-05-20 |  | Hipped Pergolas | 2025-12-19 |  | JW | Y | Y | No |  |  | Black | Clear
Scott Hay | 021 515 519 | 157 Cowan Bay Rd Warkworth | B | 2025-05-22 |  | Pitched Pergola | 2025-07-17 | 2025-07-30 | DH | Y | No | No |  | 5.9x3m | Appliance White | Light Grey
Darrell Merrie | 027 587 2964 | 72 Gunner Dr, Te Atatu Pen. | S | 2025-05-28 |  | Pitched Pergola | 2025-06-27 | 2025-07-07 | DH | Y | No | No |  | 3.9x2m | Matt Titania | Plexi- CLEAR- 2 sheets
Danny Lee | 021 1573624 | 76D Chartwell Avenue Glenfield. | S | 2025-05-28 |  | Pitched Pergola | 2025-07-02 | 2025-07-17 | DH | Y | No | No |  | 4.54x3m | Black | Plexi- Lgrey- 4 sheets
Paul Chambers | 021 051 5675 | 27 Pohutukawa Ave, Red Beach | B | 2025-06-07 |  | Pitched Pergola | 2025-07-23 | 2025-07-28 | DH | Y | No | No |  | 5.8x1.5m | Anotec Mid Bronze | Plexi- Lgrey- 2 sheets |  | SP Gutter
Ed Aitken | 0275800294 | 119 Kennedy Rd, Diary Flat | B | 2025-06-10 | y | Pitched Pergola | 2025-07-28 | 2025-08-18 | DH | Y | No | No |  | 7.5x1.8m | Black | Lgrey Plexi?- 3 sheets |  | Last pergola between house and carport- Fix leaks
Sel Miller (Norma) | 021 751 810 | 4 Kettlewell Dr, Millwater | S | 2025-06-26 |  | Electric Blinds | 2025-07-09 | 2025-08-15 | JI | Y | No | 2 |  |  | Silver Star Kinetic | N/A |  | Two Ziptrak blinds. Electric control.
Murray Rowe | 027 496 9694 | 2206 Cove Rd, Mangawhai | S | 2025-07-21 |  | Inverted Pitched | 2025-11-25 | 2025-11-28 | JW | Y | Y | No |  | 5.7x4m | Grey Friars | Crystalite 9x 5m grey |  | L Plate - Grey Frairs , Pergolas TBC
Narelle Barron | 021 1389 433 | 45 Urumaraki Ave, Helensville | S | 2025-07-06 | y | Pitched & Gable | 2025-07-04 | 2025-10-03 | DH,JI | Y | No | 2 |  |  | Black | Light Grey |  | Gable and Pitched Pergola
Brett Morris | 027 538 7704 | 3 Podgora Ave, Huapai | B | 2025-07-04 | y | Pitched | 2025-08-21 | 2025-08-28 | JW,E |  | No | 2 |  |  | Black |  |  | 200x50 Front beam
Rob Hindmarsh | 021 991 550 | 9 Miromiro St, Greenhithe | B | 2025-07-06 | y | Gable | 2025-09-12 | 2025-09-23 | DH | Y | No | no |  | 4.7x4.4m | Titania
Wallis Weir | 027 311 7735 | 27 Bellvedere Place, Warkworth | B | 2025-07-11 | Y | Pitched Pergola | 2025-09-01 | 2025-09-13 | JI,LF | Y | No | 2 |  | 6.7x3m | Titania | Lgrey Plexi- 4 sheets
Carol McKenzie | 09 627 5069 | 9 Wade St, Blockhouse Bay | S | 2025-07-14 | y | Pitched | 2025-07-23 | 2025-08-05 | JI |  | No | No |  |  | Appliance White | Plexi Clear - 1 sheet
Carolyn Mackay | 021 643 655 | 1/29 Mahara Ave, Birkenhead | B | 2025-07-14 | y | Pitched Pergola | 2025-08-18 | 2025-09-01 | JI | Y | No | No |  |  | Appliance White | Plexi Clear - 3 sheets |  | Soffit Brackets
Clegg Builders | 021 962 072 | 32 Lauren Grove, Ardmore | S | 2025-07-29 | y | Gable Carport | 2025-07-28 | 2025-09-05 | JW | Y | Y | No |  |  | Black and Tomcat (orange) | Lgrey Plexi- 9 sheets |  | Large aluminium parapit in orange
Jill Perry | 0273 929 364 | 64b Oakdale Rd, Mt Roskill | S | 2025-07-19 | Y | Pitched | 2025-08-12 | 2025-09-17 | AC |  | No | 2 |  | 7.3 x 3m | Ironsands | Plexi Lgrey - 4 sheets |  | Final blind payment 30-09-25
Andy McCowan | 021582112 | 53 Tindalls Bay Road, Whangaparoa | J |  | y | Pitched Shed | 2025-09-23 | 2025-12-01 | JW | Y | No | 1 |  |  | Gull Grey | Insulated Panels |  | Insulated panel shed
Zac Rathbone | 021 021 91090 | 3 Morrin St, Ellerslie | S | 2025-07-28 | y | Pitched Pergola | 2025-09-15 | 2025-09-23 | JW | Y | No | No |  |  | Arctic White | Light Grey - Plexi
John Sieu | 022 6858 183 | 68a Grand Drive, Remuera | S | 2025-07-28 | y | Pitched Pergola | 2025-09-08 | 2025-09-22 | JI | Y | No | No |  |  | Black | Light Grey
Russell O'Brien | 021 770 756 | 14 Mariposa Cres, Birkenhead | B | 2025-07-30 | y | Gable Pergola | 2025-10-07 | 2025-11-07 | DH | Y | 12 | 1 |  |  | Appliance White | Opal |  | Plus End Blind
Elliot Maher |  | 167a Pt Chevalier Rd | S | 2025-07-31 |  | Ziptrak Blind | 2025-08-15 | 2025-08-25 | JI | Y | No | 1
Raewyn Pilbrow | 021 445 516 | 19 Bingley Ave, Epsom | J | 2025-07-31 | y | Pitched Pergola | 2025-09-15 | 2025-09-25 | JI | Y | No | No |  | 7.3x1.5m | Appliance White | Plexi - Light Grey
John Helmink | 027 246 3534 | 45 Te Oneroa Rd, Long Bay | S | 2025-08-04 | y | Pitched Pergola | 2025-10-13 | 2025-10-30 | JW | Y | No | No |  |  | Silver Anodised | Light Grey |  | Carport
Brett Wilgar | 021 608 667 | 921B Takatu Road, Warkworth | B | 2025-08-11 | y | 2 Pergolas | 2025-10-01 | 2025-10-16 | DH | Y | No | No |  |  | Grey Friars | Crystalite 14x4m |  | Pitched and unequal gable pergola
Hubert Dang | 027 3374 411 | 30 Thornbury Crescent, East Tamaki Heights | B | 2025-08-17 | y | Pitched Pergola | 2025-10-15 | 2025-10-23 | DH | Y | No | No |  | 5.5x3.7m | Black | Opal -9x 4m sheets |  | SP Gutter - Installed before 28th October
Terry Lawrence | 027 216 4480 | 43 Bannings Way, Hobsonville | S | On Completion |  | Infill | 2025-08-28 | 2025-09-06 | JI | Y | No | No |  |  | Grey Friars | Plexi |  | Small vertical infill between posts
Christina Black | 027 631 4701 | 389 Koheroa Rd, Mercer | B | 2025-08-25 | y | Boxed Pitched Perg | 2025-10-21 | 2025-10-30 | DH | Y | No | No |  | 10.7x1.5m | Black | 3x Plexi- Light Grey |  | Boxed Perimeter
Chrissy Wadsworth-Smith | 021853900 or 021609815 | 49 Tindalls Bay Road | S | 2025-08-18 | y | Feature Wall | 2025-10-22 | 2025-11-11 | JW | Y | No | No |  |  | Sandstone Grey | Opal - 3x 5m sheets |  | Opal acyric- Cedar vertical slats
Kevin Rundle | 021 988 258 | 8 Atchison Lane, Clevedon (Otau Ridge MetlifeCare) | S | 2025-08-26 | y | Pitched inside pergola | 2025-10-28 | 2025-11-25 | AC | Y | No | 1 |  |  | Ironsands | 2x Plexi- Light Grey |  | Build inside existing pergola frame
Owen Burn | 021 610 019 | 99 Burnley Trc, Sandringham | S | 2025-08-26 | y | Pitched pergola | 2025-10-13 | 2025-10-22 | JI,ES | Y | 8 | No |  |  | Appliance White | 5x Plexi- Light Grey |  | White Lights
Carina Hunter | 021 222 6095 | 92 Beach Rd, Castor Bay | B | 2025-08-28 | y | Boxed Pitched Perg | 2025-10-24 | 2025-11-06 | JW | Y | No | No |  | 5.8x2.55 | Appliance White | Opal- 4@5m, 1@3m |  | 150x150 Posts- Box perimeter
Deborah Hay | 021 252 5742 | Unit 15 - 8 Wilk Lane, Browns Bay | S | 2025-08-30 | y | Pitched/Side Panel | 2025-10-22 | 2025-10-30 | JI | Y | No | No |  |  | Grey Friars | 4x Plexi- Light Grey |  | Side panel in 2x 4m Opal
Scott Taylor | 0222 671 963 | 14 Beaconsfield Street, Devonport | B | 2025-09-08 | y | Parallel Gable | 2025-10-28 | 2025-11-11 | DH | Y | No | Yes |  |  | Appliance White | Light Grey |  | 150x100 legs Blind final payment 3-12-25
Zones - Monique | 021 952 915 | 7 Ruapehu St, Mt Eden | S | 2025-09-10 | Y | Cantilevered Steel | 2025-10-17 | 2025-11-17 | JI,ES | Y | no | no |  | 3.6x2.8m | Charcoal | Light Grey
Bob Kilham | 027 422 3370 | 24 Vintry Drive, Huapai | B | 2025-09-11 |  | Steep Gable extending | Cancelled |  |  |  | No | No |  | 4.75x3.8m | Black | Light Grey now confirmed
Sean Preston | 021 952 646 | 60 Landing Drive, Albany | S | 2025-09-22 |  | Pitched Pergola | 2025-10-31 | 2025-12-08 | JW | Y | No | 2 |  |  | Appliance White | Light Grey
Caroline von Sierakowski | 021 830 221 | 11A Esperance Road, Glendowie | B | 2025-09-16 |  | Inverted Pitched | 2025-11-06 | 2025-12-04 | AC | Y | 10 | No |  | 10x3m | Black | Light Grey |  | Inverted pitched
Tim Hill | 021 614 600 | 107 Waller Road, Mauku, Pukekohe 2678 | B | 2025-09-15 |  | Boxed gable | 2025-11-06 | 2025-11-13 | DH | Y | No | No |  | 2.7 x 3m | Black | 4x Plexi- Light Grey
Tony Oldham | 021 853 189 | 2/251 Oceanbeach Rd, Mt Maunganui | B | 2025-09-11 |  | Pitch and hip | 2025-11-24 | 2025-12-06 | DH | Y |  |  |  |  | Black | Opal 5x5m
Josy Campbell | 027 643 4258 | 48a Wilson Rd, Warkworth | S |  |  | Electric Blinds | 2025-10-03 | 2025-10-13 | SC | Y | 2 |  |  |  | Black | N/A |  | 2x Ziptrak ONE - Midnight mesh with electric motors
Pro Projects Ltd | Helen 0273089247 | 82 Frank Nobelo Dr, Howick | S | 2025-09-16 |  | Gable Pergola | 2025-11-25 | 2025-12-17 | AC | Y | Yes | No |  |  | Appliance White | Light Grey Plexi
Bryce Mills | 021 116 3500 | 25a Cormack St, Mt Roskill | S | 2025-09-20 |  | Blinds only | 2025-10-02 | 2025-09-29 | JI | Y | No | 2 |  |  | Black |  |  | Two Ziptrak blinds to existing pergola
Josy Campbell | 027 643 4258 | 48a Wilson Rd, Warkworth | S | 2025-09-19 |  | Plexi on timber pergola | 2025-10-01 | 2025-10-13 | JW | Y | No | No |  |  | Black | Plexi Light Grey
Mel Bell | 021 210 9035 | 20a Reidy Pl, Pukekohe | S | 2025-09-22 | Y | Electric Awning | 2025-11-20 | 2025-12-05 | DH | Y | No | No |  |  | Black | N/A |  | Electric Awning inside pergola
Carolyn Ryan | 022 327 3099 | 50 Pukeora Ave, Remuera | B | 2025-09-22 | Y | Pitched Pergola | 2025-11-06 | 2025-12-05 | JW |  | No | 1 |  | 7.9x2.5m | Flaxpod | Light Grey Plexi |  | Steel front beam - 150x150 posts - side infill with one blind
Hugh Litchfield | 027 492 2424 | 157 Kimptons Rd, Brookby | S | 2025-09-25 |  | Pitched Pergola | 2025-12-08 | 2025-12-22 | Ali | Y | No | No |  | 6x3.5m | Titania Satin | Opal 10x 4m | Y | Aluminium doors on three sides
Steve & Denise Bowen | 0273636496 Denise or Steve 02041382332 | 31B Harvey St, Tauranga | B | 2025-09-24 |  | Parallel Box Gable | 2025-11-11 | 2025-11-21 | DH | Y | No | No |  | 5.5x3.5m | Appliance White | Grey Plexi |  | Box Perimeter with gable inside
Ralph Dias | 021 908 752 | 29 New Windsor Rd, Avondale | B | 2025-09-25 |  | Blinds only | 2025-11-13 | 2025-11-24 | ES | Y | No | 2 |  |  | Black | N/A |  | Black Frame. Mesh blinds Front and side
Dennis Covey | 027 452 0240 | 2/27b Ewington Ave, Mt Eden | S | 2025-09-29 |  | Pitched Pergola | 2025-11-03 | 2025-11-21 | JI | Y | No | 1 |  | 6x2.7m | Black | 3x Plexi- Light Grey |  | One blind. Side infill Blind install 19/01/26
Sayburn Miller | 021 851 108 | Site: 80 Bassett Rd, Remuera | S |  |  | Inclosed Pitched | March 2026 |  |  |  |  | No |  | 6mx5m | Black | Crystalite 10x 6m grey? |  | Inclosed pitched pergola over pool with louvres and door
Dale Smith | 0275382501 | 296 Point Wells Rd, Omaha | B | 2025-09-29 |  | Acrylic and joiners only | 2025-11-14 | 2025-11-18 | JI,ES | Y | No | No |  |  | Black | Crystalite 12x 5m grey | Y | Attach joiners to existing rafters
Lisa Darragh | 0211922400 | 13 Spinnaker Drive Te Atatu Peninsula | B | 2025-10-03 |  | Pitched Pergola | 2025-11-18 | 2025-11-24 | DH | Y | No | No |  | 5.8x3m | Grey Friars | Opal 9x3m | Y | Pergola only. Blinds later
Christy Traynor | 021990609 | 27 Birman Close, Half Moon Bay. | B | 2025-10-03 |  | Pitched Pergola | 2025-11-14 | 2025-11-26 | AC | Y | No | No | Y | 5.3x3.1 | Black | 3x Plexi- Light Grey |  | 3x blinds. Infill on one end only
Jill Perry | 027 392 9364 | 64b Oakdale Rd, Mt Roskill | S | 2025-10-14 |  | Blind and post | 2025-11-13 | 2025-11-19 | ES | Y | No | 1 |  |  | Ironsands | N/A |  | 100x50 Post and Ziptrak blind to match other 2
William Reader | 021 027 337 90 | 13a Garadice Rd, Rothesay Bay | B | 2025-10-06 |  | Pitched Pergola | 2025-12-15 | 2025-12-22 | DH | Y | No | No |  | 9m x 3.9m | Ironsands | Crystalite 14x 4m grey |  | 150x150 Posts
Ian Francis | 027 555 8951 | 9 The Grove, Titirangi | S | 2025-10-07 |  | Pitched Pergola | 2025-11-20 | 2025-12-29 | JI | Y | No | No |  | 6.47x3m | Arctic White | 3x Plexi- Light Grey plus 1 |  | Pitched Pergola on deck
Cam Greig, Beth McKay | 027 22 22 572 | 34 Newell St, Pt Chevalier | B | 2025-10-12 |  | Pitched Pergola | 2025-12-01 | 2025-12-08 | JW | Y | No | No |  |  | Ironsands | Clear Crystalite |  | Twisted Pitched Pergola (Pergola only at this stage)
Grace Kennedy | 022 383 2285 Andrew | 5 Acton Pl, Avondale | S | 2025-10-14 |  | Inverted Pitched | 2025-11-14 | 2025-11-24 | JW | Y | No | No |  |  | Black | Crystalite 8x 6m grey |  | Inverted Pitched pergola over deck. Sleeve over some existing posts
Catherine (DBS Landscaping) | 021 063 2684 | 10a Hallam St, Mt Albert | S |  |  | Pitched Pergola | 2025-12-15 |  | JW |  | 8 | 3 |  |  | Black | 3x Plexi- Light Grey |  | Pitched Pergola with lights and 3 blinds across two sides
Robbie Butterworth | 021 158 7039 | 37D William Potter Lane, Karaka | S | 2025-10-29 |  | Pitched and WaveShade | 2025-12-08 | 2025-12-14 | JW | Y | No | No |  |  | Black | Plexi- Light Grey |  | Pitched Pergola with WaveShade
Jane Aickin | 027 878 7907 Jane or 021 897 888 David | 16 Rosecamp Rd, Beach Haven | B | 2025-10-17 |  | Boxed Gable | 2025-12-08 | 2025-12-24 | DH | Y | Yes | No |  | 6m x4m | Appliance White | Plexi - Light Grey 5x
Maria Vince | 027 226 8810 | 95d Peary Rd, Mt Eden | B | 2025-10-21 |  | Pitched Pergola | 2025-01-12 | 2026-01-28 | DH | Y | 14 | no |  | 7.9x4m | Black | Crystalite 10x 4m Clear | Y | 14 black lights. Confirmed Clear sheets.
Susan Murray | 021 324 177 | 39a Hasting Rd, Mairangi Bay | S | 2025-10-28 |  | Pitched | 2025-12-04 | 2025-12-20 | JI | Y | No | No |  | 4.25 x 3m | Black TBC | 2x Plexi- Light Grey plus 1 bay
Andrew Leys | 021 289 8844 | 311 Pt. Chevalier Rd | B | 2025-10-30 |  | Omni Blind | 2025-11-18 | 2025-11-23 | JW | Y | No | 1 |  |  | Omni Blind Urban Quartz colour | N/A |  | Blind under existing pergola
Juliet Fleischl | 021 264 3165 | 45i Habour View Rd, Pt Chev | S | 2025-10-30 |  | Omni Blind | 2025-11-18 | 2025-12-12 | JW | Y | No | 1 |  |  | Omni Blind Urban Iceberg colour | N/A |  | Blind under existing pergola
Johanna Smith | 021 024 10524 | 246 Mill Flat Rd, Riverhead | J | 2025-10-30 |  | Freestanding Gable |  |  |  |  | Yes | 1 |  | 5.5x4.2m | Black | Colour steel | Y | Gable with full colour steel roof and timber sarking underneath
Rachel Commons | 021 0756818 | 25 Rahui rd Greenhithe | B | 2025-10-31 |  | Gable | 2026-01-28 | 2026-02-25 | DH | Y | 18 | No |  | 6mx6m | Black | 6x Plexi- Light Grey |  | 20 degree gable
Carolyn Thomson | 0210726707 | 6/59 Rangatira Road, Beach Haven | B | 2025-11-06 |  | Pitched | 2025-11-17 | 2025-12-01 | JI | Y | No | No |  | 4.1 x 3.2 | Appliance White | Plexi - Light grey |  | Max out Plexi sheets
Natalie Sparg | 027 363 4437 | 2/3 Roanoke Way, Albany | S | 2025-11-21 | Y | Small Pitched Pergola | 2025-12-16 |  | ES | Y | No | No |  | 1.8 x 1.6m | Karaka | Plexi - Light grey |  | Small entry pergola
Zones - Kate Ryan | 021 204 8019 Vaughan | 21A Ashby ave, St Heliers. | J | 2025-11-21 | Y | Pitched Pergola | 2026-02-09 |  | DH |  | No | No |  | 5.5 x3m | Matt Lignite | Clear Plexi 3 sheets
Camila Gallo | 021 195 5881 | 241b Rangatira Road, Beach Haven | B | 2025-11-11 |  | Roof Blind | 2025-11-18 | 2025-11-20 | JW | Y | No | 1 |  | N/A | Black |  |  | Gable - Omni wire blind on one side
Carolyn Lawrence | 027 472 0555 | 28 Kawerau Ave, Devonport | S | 2025-11-11 |  | Pitched Pergola | 2025-12-10 | 2025-12-16 | JI | Y | No | No |  | 5.8x2.8m | Appliance White | Plexi- 3 x grey
Rhonda Moir | 027 358 2884 | 46 Landscape Rd, Mt Eden | B | 2025-11-13 |  | Pitched Pergola | 2025-11-27 | 2025-12-05 | JI | Y | No | No |  | 6.7x1.8m | Black | Plexi- 3 x grey |  | White soffit brackets
Brad Findlay | 021982158 | 30 Graham Rd, St Heliers | B | 2025-11-13 |  | Pitched Pergola | Engineers PS1 |  |  |  | Yes | No |  | 6.83x3.1m | Black | Plexi- 4 x grey |  | Mask and spray existing steel posts to match pergola
Martine Gibson | 021 235 0550 | 113 Selwyn Ave, Mission Bay | S,J | 2025-11-14 |  | Large Gable | Council Consent |  | DH |  | Yes | No |  |  | Appliance White | 25 x 4m Opal |  | Glass louvres
Jamie France | 021 909 987 | 20 Sudeley St, Orakei | S | 2025-11-21 |  | 3x Omni Blinds | 2025-12-15 | 2025-12-22 | JI | Y
Mark Scowen | 021 246 8367 | 46 Kumukumu Rd, Long Bay | S | 2025-11-21 |  | Pitched Pergola | Febraury |  | JW |  | No | TBC |  |  | Black | 4x 6m grey, 1x 3m grey | Y | Connect to existing SP pergola
Patricio Castellano | 022 4200 375 | 1/86 Seaview Rd, Castor Bay | B | 2025-11-23 |  | Pitched Pergola | 2026-02-11 |  | JW |  | No | 2 |  | 2.8mx2.4 | Appliance White | 2x Plexi Light Grey
Alex Santos | 021 112 6421 | 29a Victor St, Avondale | B | 2015-11-24 |  | Pitched Pergola | 2026-02-09 | 2026-02-19 | JI | Y | no | no |  |  | Ironsands
Ross Currie | 022 384 4522 | 20 Kinross St, Blockhouse Bay | B | 2025-11-27 |  | Pitched Pergola | 2026-01-06 | 2026-03-01 | JI,ES | Y | No | No |  |  | Appliance White | 8x Crstalite grey | Y
Ann Batten | 0274 570 828 | 471 Whitford-Maraetai Rd, Whitford | S | 2025-11-28 |  | Large Gable | 2026-03-10 |  | AC,AK |  | No | 1 |  |  | Ironsands | light grey |  | Large gable with two triangular infills
Jeremy Skinner | 0225 434 535 | 158 Ladies Mile, Ellerslie | S | 2025-12-05 |  | Gable pergola | 2026-02-12 | 2026-03-09 | DH | Y | Y | TBC |  |  | Black | Plexi - Light grey
Steve Lewis (CAPE Construct) | 021 325 204 | 11 Westhaven Dr, CBD | S | 2026-01-28 |  | Gable Glasshouse | 2026-01-19 | 2026-02-28 | DH | Y | TBC | No |  |  | Black | Plexi - Light grey
Jennifer Partridge | 021 029 19097 | 14a Littlejohn St, Hillsborough | S | 2025-12-10 |  | Gable Carport | 2026-02-16 | 2026-03-01 | JI | Y | No | No |  |  | Appliance White | Plexi - Light grey TBC
Sadhana Zhen | 021 217 3790 | 132a Terry St, Blockhouse Bay | B | 2025-12-10 |  | Pitched Pergola | 2026-02-23 | 2026-02-25 | JI | Y | No | No |  |  | Appliance White | 4x5m, 1x3m Opal | Y | Soffit brackets. 1x post
Suzanne Follas | 021 486 535 | 3 Barcliff Terr, Gulf Harbour | B | 2025-12-14 |  | Pitched Pergola |  |  |  |  | No | No |  |  | Appliance White | Panels TBC
Andrew Baker | 021 648 953 | 4 Third Ave, Kingsland | B | 2025-12-22 |  | Pitched /Gable | 2026-03-02 |  | JI,AK |  | No | Yes |  |  | Appliance White (Confirmed) | Crystalite Grey |  | (Sheets 7x5m 3x6m)
Edmond Lee | 021 255 3455 | 40 Golfland Drive, Golflands, Howick | B | 2025-12-29 |  | 2x Gables | 2026-03-10 |  | JI |  | Y | No |  |  | Black and Ironsands | 11x 5m Opal - 1.5x Plexi
Carl Mills | 027 673 2275 | 9 Otau Mountain Rd, Clevedon | S | On Completion |  | Extra panels | On hold |  |  |  | No | No |  |  | Appliance White | 2x grey 5m crystalite |  | 3x Joiners and 2x panels only only existing pergola
Bill Kingsley | 021 0676304 | 14 Sudeley Street, Orakei | S | 2026-01-30 |  | Gable Pergola | March or sooner |  |  |  | No | No |  |  | Appliance White | Crystalite Grey |  | 40 degree pitch. Run draw wire for future light
Fiona Murray | 021 437 000 | 9 Bennett St, Mt Albert | B | 2026-02-09 |  | Pitched Pergola |  |  |  |  | No | No |  |  | Appliance White | Crystalite Grey
Rhonda Moir | 0273582884 | 46 Landscape Rd, Mt Eden | S | 2026-02-02 |  | Blinds / Infill | 2026-02-26 |  | JI,AK |  | No | 3 |  |  | Black |  |  | 3x Blind and infill or flashing
BTS Construction | Mark 0223014096 | 82 Langan Ave, Browns Bay | S | On Completion |  | Sheets and joiners only | Deliver only | 2026-02-28 |  |  | No | No |  |  | Black | Crystalite Grey 7x5m |  | Sheets and joiners only. Rubbers end caps and delivery
Neil Hilton | 027 627 1713 | 99 Te Pua School Rd, Helensville | B | 2026-02-19 |  | Pitched Pergola |  |  |  |  | No | No |  |  | Ironsands | Crystalite Opal 16xOpal
Mary Jones | 021 121 7466 | 17 Currell Way, Somerville, Auckland | B | 2026-02-24 |  | Gable Pergola |  |  |  |  | 12 | 1 |  |  | Black | Plexi Light Grey (7 sheets) |  | Large gable. Infill both ends
Steve Hooper | 027 453 2577 | 66 Duke St, Mt Roskill | S | 2026-03-02 |  | Pitched Pergola |  |  |  |  | No | No |  |  | Appliance White | Plexi Light Grey |  | Front entry pergola. Gutter on rear pergola
Jason Watson | 022 127 0864 | 46 Esther Pl, Red Beach | B | 2026-03-04 |  | Gable Pergola |  |  |  |  | No | No |  |  | Ironsands | Plexi Dark Grey (3plus1) |  | 150x150 legs. Upper deck
Kane Quinn | 021 292 6855 | 5 Capriana Drive, Karaka | B | 2026-03-05 |  | Gable/Pitched Combo |  |  |  |  | No | No |  |  | Ironsands | Plexi Light Grey
Karel Boonzaaijer | 021376969 | 226 Greenhithe Road, Greenhithe | S | 2026-03-10 |  | Pitched Pergola | Before end of April |  |  |  | No | No |  |  | Appliance White